Maa's Inspiration Inc.: 12-Month Fundraising Plan

Love All, Serve All

Prepared for: Aslam Hemani, Director · Date: October 13, 2026 · Plan period: November 2026 to October 2027

Status: DRAFT. Nobody has been contacted. No email has been sent. Every letter in this plan is a draft for Aslam to approve.

| Organization facts used |  |
| --- | --- |
| Legal name / status | Maa's Inspiration Inc., 501(c)(3), EIN 86-2221897, Carrollton TX, serving DFW |
| Contact | Aslam Hemani, Director · aslam@maasinspiration.org · 214-517-1938 |
| Maa's Meals (open) | About 2,200 fresh hot meals every Saturday (10 AM to noon), 1445 MacArthur Dr Suite 104, Carrollton 75007 · 120+ senior families weekly · 100,000+ meals a year · about 50 volunteers · 5+ years · about $5 per meal · 100% of donations fund meals, no salaries |
| Maa's Place (opening soon) | Free senior center, ages 55+, Mon to Thu 10 AM to 2 PM, 2700 Old Denton Rd Suite 102, Carrollton 75006 · no transportation |
| Blooming Star Village (coming soon) | Free day program for children 5 to 17 with special needs, Mon to Thu 9 AM to 2 PM, same address · opening date TBA |
| Story and motto | In memory of Maa (Gulbano), whose greatest joy was feeding others · Love All, Serve All |
| Unknowns (placeholders) | Annual operating budget [$] · Amount raised last year [$] · Number of donors [#] · 12-month goal [$] · Board members [names] |

Owners used in this plan. Aslam (decides, signs, makes the personal asks) · Staff (named by Aslam) · Volunteer (trained role) · Assistant (Grok Bot: research, drafts, trackers, reports; never contacts anyone or sends anything without Aslam's approval).

Verification. Every funder, rule and date was checked on the web on October 13, 2026 and has a link. Anything not confirmed is marked Unverified. The full check log is in the appendix.

# The Plan on One Page

Headline: Maa's Inspiration has a powerful, simple story ($5 = one hot meal, 2,200 meals every Saturday, 100% to meals). The biggest gains in year one come from fixing the donate page, building monthly giving, thanking fast, and asking the community you already have. Grants come second and take longer.

| # | Do this | Why | Owner | When |
| --- | --- | --- | --- | --- |
| 1 | Fix the donate page (monthly button, custom amounts, program tags, receipt wording) | The "Monthly" button does not create a monthly gift today, and custom amounts are changed at checkout | Assistant drafts, Aslam approves | Nov 2026 |
| 2 | Launch Maa's Circle monthly giving ($25/month = 5 hot meals a month) | Monthly gifts are steady, predictable income, and monthly donors tend to stay longer | Aslam / Assistant | Nov 2026, then monthly |
| 3 | Thank every gift within 48 hours; Aslam calls every gift of $250+ | Fast thanks is the cheapest way to get a second gift | Staff / Aslam | Starting now |
| 4 | Run 5 seasonal campaigns: Giving Tuesday/year-end, Maa's Place opening, Ramadan, Maa's Day (Mother's Day), North Texas Giving Day | Each matches a natural giving moment for this community | Aslam / Assistant | See calendar |
| 5 | Hold one signature event: Love All, Serve All Community Dinner (May 2027) | Brings donors, sponsors, and volunteers into one room | Aslam + Volunteer lead | May 2027 |
| 6 | Sign up local business sponsors with simple tiers | Restaurants and businesses already support the mission | Aslam | Jan to Mar 2027 |
| 7 | Apply to 8 to 10 well-fit grants (Walmart now, food bank partnership, Dallas Foundation, Meadows, Moody, CDBG) | Steady money plus free or low-cost food | Assistant drafts, Aslam submits | Rolling |
| 8 | Track it in one donor database (Little Green Light, $45/month) linked to Stripe | You cannot thank, segment, or report without it | Assistant / Staff | Nov 2026 |

Estimated 12-month potential: about $86,500 (low) to $405,500 (high). These are estimates for planning, not promises. The real number depends on how many donors you have today [#] and how much was raised last year [$]. Suggested working goal: [12-month goal $], set by Aslam after he fills in those two numbers.

# 1. Website Review and Fundraising Ideas

## 1(a) What helps and what hurts donations on the new site

I fetched and reviewed the preview pages on October 13, 2026: home, donate, meals, maas-place, blooming-star-village, get-involved, volunteer, and contact. I also read the donate page code.

What already helps

Clear impact math: $5 = one hot meal, $25 = a senior meal pack, $100 = a full delivery run for 20 people.

Strong trust signals: 501(c)(3), EIN shown, "secure payment via Stripe," "100% of donations fund meals."

One-time / Monthly toggle, tribute ("in honor of") giving, an FAQ, "Other ways to give," and a thank-you to named partners (Al Markaz Restaurant, Dare 2 Inc, Texas Wholesale, Popeyes Chicken, Chef Chen).

The Maa's Place page links to donate.html?program=maas-place, and the code passes the program to Stripe as client_reference_id, so those gifts can be tracked by program.

The Meals page tells Maa's story and has a real weekly video. That is the best fundraising asset on the site.

What hurts (and the fix)

| # | Issue found | Why it costs money | Fix | Owner | Effort |
| --- | --- | --- | --- | --- | --- |
| 1 | The "Monthly" button changes nothing. The code only highlights the button. One-time and monthly both open the same 7 Stripe Payment Links. | Monthly donors may be charged once, with no recurring gift. Monthly giving is the core of this plan. | Create 4 to 5 recurring Stripe Payment Links ($10, $25, $50, $100/month plus "choose amount") and have the toggle switch to them. First check in Stripe whether the current 7 links are one-time or recurring. | Assistant (code) / Aslam (Stripe) | Low |
| 2 | Custom amounts get changed. A $75 gift opens the $50 link with quantity 2 ($100). A $30 gift becomes $25. | Donors see a different amount at checkout and leave. It can also hurt trust. | Add one Stripe link with "customer chooses what to pay" and send all custom amounts there. | Assistant / Aslam | Low |
| 3 | Low starting point. The form opens at $5 and the preset buttons are $50 to $500, with no $25 button. | People anchor on the first number they see. | One-time: $25 / $50 (pre-selected) / $100 / $250. Monthly: $10 / $25 (pre-selected) / $50 / $100. Put an impact line under each. | Assistant | Low |
| 4 | Program tags are missing on 2 of 3 program pages. Blooming Star Village and Meals link to plain donate.html, so those gifts are tagged "general." | You cannot report "raised for BSV" to donors or funders. | BSV buttons go to donate.html?program=bsv; Meals buttons go to ?program=meals. Add a 4-choice picker on the donate page: Meals / Maa's Place / BSV / Where most needed. | Assistant | Low |
| 5 | Donate page copy is meals-only. "100% ... goes directly toward our meal program" shows even when someone gives to Maa's Place or BSV. | Confusing, and it can create a restricted-gift problem. | Change the heading and impact lines based on ?program=. Ask Aslam how to word the 100% claim for Maa's Place and BSV (see Questions). | Assistant / Aslam | Low |
| 6 | Receipt wording. The FAQ says the Stripe email receipt "serves as your official acknowledgment for tax purposes." | For gifts of $250+, the IRS requires a written acknowledgment that says whether any goods or services were given. Stripe's standard receipt does not say this unless you add it. | Add this line to Stripe receipts: "No goods or services were provided in exchange for this contribution. Maa's Inspiration Inc., EIN 86-2221897." Also send our own thank-you letter (Section 4). | Aslam (Stripe settings) | Low |
| 7 | Wrong drop-off place for in-kind items. The FAQ says drop items at "MAA's Place during volunteer hours." Maa's Place is not open, and it is at a different address. | Lost food donations and confused donors. | "Drop off Saturdays 10 AM to noon at 1445 MacArthur Dr Suite 104, or email to arrange." | Assistant | Low |
| 8 | No mail-a-check, donor-advised fund (DAF), or employer match info. | Bigger gifts often come by check or DAF, especially in Nov and Dec. | Add: "Checks payable to Maa's Inspiration Inc., [mailing address]" · "Give from your DAF: Maa's Inspiration Inc., EIN 86-2221897" · "Ask your employer to match your gift." | Assistant | Low |
| 9 | No story or photo on the donate page. | A face and one sentence beat any statistic. | Add 1 photo (consent on file) + 2 sentences + the weekly video. | Assistant / Aslam | Low |
| 10 | Forms send to a personal Gmail (honor, volunteer, and contact forms go to aslamhemani@gmail.com through FormSubmit). | Donor privacy and continuity risk. Records get scattered. | Send forms to aslam@maasinspiration.org (or a shared org inbox). Add a short donor privacy statement. | Aslam | Low |
| 11 | No email sign-up. | You can't send an impact update to someone you can't reach. | Add a "Get our monthly impact update" box to the home, meals, and donate pages. | Assistant | Low |
| 12 | "Become a Partner" has text but no clear next step. | Businesses ready to help have nowhere to click. | Add a button: "Become a sponsor" leading to tiers (Section 2) and an email link. | Assistant | Low |
| 13 | Content rule check. The Meals page says "Driven by faith, compassion..." | It conflicts with the no-religion rule for public content. | Change to "Driven by compassion and a deep sense of responsibility..." | Assistant / Aslam | Low |
| 14 | Small fixes: "~50 Volunteers (about 50)" says it twice; the Meals page counters show 0 until they animate. | Looks unfinished. | Use "About 50 volunteers"; show real numbers if the animation does not run. | Assistant | Low |

Keep consistent with the social media plan. The donation QR in every video points to https://maasinspiration.org/donate.html (that page answers today). When the new site goes live, keep that exact address working, so the QR codes in the videos never break.

## 1(b) Campaign and event ideas

| Idea | Effort | Expected return | Cost | Best time | Owner |
| --- | --- | --- | --- | --- | --- |
| Fix donate page + monthly ask | Low | High | $0 | Nov 2026 (before Giving Tuesday) | Assistant + Aslam |
| Maa's Circle monthly giving | Low | High | $0 | Launch Nov 2026; push every month | Aslam / Assistant |
| Sponsor-a-Senior ($25/wk pack = ~$100/mo) | Low | Med-High | $0 | Thanksgiving + Mother's Day | Assistant |
| Sponsor-a-Meal / Sponsor-a-Saturday route | Low | Medium | $0 | Year-round; businesses | Aslam |
| Giving Tuesday + year-end appeal | Medium | High | $500-$1,500 | Dec 1-31, 2026 | Aslam / Assistant |
| Maa's Place opening 'Founding Friends' | Medium | High | $500-$2,000 | 8 weeks before opening [date TBA] | Aslam / Staff |
| Ramadan 'Share a Meal' (via faith partners) | Medium | High | $200-$800 | ~Feb 8-Mar 9, 2027 | Aslam |
| Diwali + Thanksgiving 'Share a Plate' | Low | Medium | $200-$500 | Nov 2026 | Aslam / Volunteer |
| Maa's Day (Mother's Day) tribute gifts | Low | Medium | $300-$800 | Apr 19-May 9, 2027 | Assistant |
| Annual Community Dinner 'Love All, Serve All' | High | High | $5k-$15k | May 2027 (week of Maa's Day) | Aslam + Volunteer lead |
| North Texas Giving Day | Medium | Medium | $0-$300 | Aug 27-Sep 16, 2027 | Assistant / Aslam |
| Peer-to-peer + birthday fundraisers | Low | Low-Med | $0 | Year-round; NTxGD season | Volunteer |
| Restaurant give-back nights | Low | Low | $0-$200 | Every other month | Volunteer |
| Business sponsorship tiers | Medium | Med-High | $300 | Jan-Mar 2027 (budget season) | Aslam |
| Raffle (optional, at Community Dinner) | Medium | Low-Med | $0 if prize donated | May 2027 | Staff (unpaid) |

How each main campaign works (step by step)

Maa's Circle (monthly giving). 1) Fix the monthly links (Issue 1). 2) Name the levels: $10 = 2 meals a month, $25 = 5 meals, $50 = 10 meals, $100 = Sponsor-a-Senior. 3) Ask current one-time donors first (letter template, Section 3). 4) Show a "Maa's Circle" line in every social Post 3 (Donation Impact). 5) Send members a monthly 60-second video update. Goal: 40 monthly donors by Dec 31, 2026, and 100 by Oct 2027 [confirm].

Sponsor-a-Senior / Sponsor-a-Meal. $25 feeds one senior family for a week (about 5 meals). $100 a month sponsors one senior family. A business can "Sponsor a Delivery Run" ($100 = hot meals for 20 people) or fund a tenth of a Saturday ($1,100 = 220 meals). No names of seniors are shared. Donors get a first-name-only or anonymous story, with consent.

Maa's Place opening "Founding Friends." 1) Aslam fills in the opening budget (Section 5). 2) Set a goal equal to opening costs plus 3 months of running costs. 3) Founding Friend = $1,000+ (name on a "Founding Friends" wall). Room or activity sponsors (chai corner, exercise corner, game table) at [$] each. 4) Soft-launch with 10 close supporters before going public. 5) Invite donors to a ribbon cutting and tour. Best time: the 8 weeks before opening [date TBA].

Giving Tuesday and year-end. Giving Tuesday is Tue Dec 1, 2026. Ask 1 or 2 businesses for a match ("every gift doubled up to $[X]"). Mail a letter by Dec 3. Send emails Dec 1, 15, 29, and 31. Post videos on Dec 1 and Dec 31 (already in the social plan).

Ramadan (about Feb 8 to Mar 9, 2027, by moon sighting). Faith communities are welcome as funders. Run it through partner mosques and community groups, using their channels: "Share a Meal: $5 feeds a neighbor, $500 sponsors 100 meals." On public social media, keep the wording non-religious ("this season of giving"), per the content rule.

Diwali (Sun Nov 8, 2026) and Thanksgiving (Thu Nov 26, 2026): "Share a Plate." Partner temples and businesses run a food or fund drive. Volunteers collect at events. Use Sponsor-a-Senior as the ask.

Maa's Day (Mother's Day, Sun May 9, 2027). This is the signature campaign. "Honor your mother the way Maa would: by feeding someone." Tribute gifts send an e-card to the mother being honored (the tribute form already exists). It runs Apr 19 to May 9 and leads into the Community Dinner.

Love All, Serve All Community Dinner (May 2027). A simple, home-style dinner, not a black-tie gala. 150 to 250 guests. Tickets [$] with a quid pro quo disclosure printed on them. Table sponsors, a 5-minute story, one live ask ("Fund a Saturday"), and an optional raffle (rules in Section 5). Budget $5,000 to $15,000. Aim for 3 times the cost or better.

Peer-to-peer and birthday fundraisers. Volunteers and donors set up personal pages ("For my birthday, help me serve 200 meals"). Use your CRM's or Givebutter/Zeffy's free peer-to-peer pages, or the North Texas Giving Day page (it supports fundraisers). Give each fundraiser a one-page kit with a photo, 3 captions, and the QR code.

Restaurant give-back nights. Start with existing partners (Al Markaz, the Popeyes franchise partner, Chef Chen). Ask for 15% to 25% of the night's sales or a fixed gift. Chipotle gives 25% of qualifying sales (applications reopen March 2027). Hold one every other month.

North Texas Giving Day: Thu Sep 16, 2027 (verified). 2027 registration opens Nov 2, 2026. Communities Foundation of Texas covers card fees. Secure a match pool from sponsors by July. Recruit 10 peer-to-peer captains. Early giving likely opens in late August (in 2026 it opened Aug 27).

# 2. Other Funding Sources

## 2(a) Recommendations

1.  Start with food, not just cash. A food bank partnership (North Texas Food Bank for Dallas County clients, or Tarrant Area Food Bank for Denton County) can cut the cost per meal. NTFB reviews applications in January, April, July, and October.

2.  Apply now to quick, small corporate grants. Walmart Spark Good local grants ($250 to $5,000) are open until Nov 30, 2026. Kroger, Albertsons/Tom Thumb, H-E-B, and Sprouts follow.

3.  Build relationships with 4 or 5 foundations that take open applications: the Dallas Foundation (summer cycle), Meadows, Moody, and Rees-Jones (BSV, once it opens). Several large funders are invitation only (CFT, TI, Toyota, AT&T). For those, the route is relationships, not applications.

4.  Use the local network: Carrollton-Farmers Branch Rotary, faith communities, restaurants, and employers with matching gifts.

5.  Be honest about eligibility. Hoblitzelle needs an audit and a budget over $250,000. Crystal Charity Ball needs 3 years of serving children. Some Dallas Foundation cycles need a budget over $500,000. Don't spend time there until you qualify.

## 2(b) Funders and programs (all checked Oct 13, 2026)

| # | Funder / link | Fits | What they fund · watch-outs | Typical size | Timing / deadline | Status | Next step (owner) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | North Texas Giving Day 2027 (Communities Foundation of Texas) northtexasgivingday.org | All | Online giving day for nonprofits serving 20 North Texas counties; CFT covers card fees. Watch: 2027 registration rules/fees not yet posted | Depends on our donors + any match pools; est. $5k-$20k | Registration opens Nov 2, 2026; Giving Day Thu Sep 16, 2027 (early giving ~late Aug) | Verified | Register in Nov 2026; recruit a match sponsor by Jul 2027 (Assistant (prep) / Aslam (submit)) |
| 2 | Communities Foundation of Texas - Nonprofit Gateway Profile cftexas.org | All | Grants are now nearly all invitation-only; profile puts us on CFT's radar (also DAF holders). Watch: Needs 501(c)(3) active 2+ yrs; 50%+ served in eligible counties | Unverified (third-party listings say $5k-$50k) | Rolling profile; no open application | Verified | Complete Gateway Profile in Nov 2026 (Assistant (draft) / Aslam) |
| 3 | The Dallas Foundation - Summer Grants Cycle (Family Economic Stability & Critical Needs) dallasfoundation.org | Meals, Maa's Place | Essential services for children, families, older adults in Dallas County; general operating OK. Watch: Over 50% of clients must live in Dallas County; asks for 990, budget, audited financials if available; no event underwriting | $5,000-$75,000 (2026 cycle) | 2026 window was Jun 10-26 (closed). 2027 dates not posted - expect ~June 2027 (Unverified) | Verified | Confirm county mix; watch page from Apr 2027 (Assistant) |
| 4 | The Dallas Foundation - Spring cycle (Specialized Health & Disability) dallasfoundation.org | BSV (later) | 2026 spring focus incl. specialized health & disability programs. Watch: 2026 spring cycle required org budget over $500,000; BSV not open yet | Unverified | 2026 window was Jan 14-28; 2027 not posted | Verified | Revisit after BSV opens (Assistant) |
| 5 | The Meadows Foundation - Human Services mfi.org | Meals, Maa's Place | Programs that improve quality of life for vulnerable Texans; up to 50% of giving in DFW. Watch: Wants measurable outcomes and other funding secured | Unverified | Rolling; submit 4-5 months before funds are needed; monthly info sessions | Verified | Attend an info session; call program officer (Aslam's decision) (Aslam / Assistant) |
| 6 | The Rees-Jones Foundation rees-jonesfoundation.org | BSV (children & families) | DFW children, youth and their families (and companion animals) within defined portfolios. Watch: Must match a portfolio; BSV must be operating | Unverified | Rolling Letter of Inquiry; ~30 days to invite/decline; ~4 months staff review | Verified | Check portfolio fit; LOI after BSV opening date is set (Assistant) |
| 7 | The Moody Foundation - General Grant Inquiry moodyf.org | All | Texas: education, social services & family well-being, health & wellness, arts. Watch: One active inquiry per organization | Unverified | Rolling inquiry; up to ~6 months to decision; 4 trustee meetings/yr | Verified | Submit one inquiry (Maa's Place opening) in Jan 2027 (Assistant (draft) / Aslam) |
| 8 | Hoblitzelle Foundation hoblitzelle.org | Maa's Place / BSV capital | Capital only: buildings, renovation, equipment, vehicles, technology (Dallas area priority). Watch: Requires annual budget over $250,000 AND external audit within 2 years - likely NOT eligible yet | Unverified | Windows Feb 15-Apr 15, 2027 and Jun 15-Aug 15, 2027 | Verified | Ask Aslam: budget size and audit status (Aslam) |
| 9 | Crystal Charity Ball crystalcharity.org | BSV (future) | Dallas County children's charities; large multi-year project grants. Watch: Must have served Dallas County children 3+ years - BSV not eligible until ~3 yrs after opening | Unverified | 2027 cycle closed Oct 8, 2026; next cycle ~Aug-Oct 2027 | Verified | Long-term only (Assistant (track)) |
| 10 | Walmart Spark Good Local Grants walmart.org | Meals | Local store/Sam's Club/DC grants; hunger relief is a frequent area of support. Watch: Needs Spark Good account + Deed verification; one award per facility per fiscal year | $250-$5,000 | FY27 Cycle 3: Aug 1-Nov 30, 2026 (open now). Cycles 1-2 were Feb 1-Apr 15, May 1-Jul 15 | Verified | Apply to 2-3 Carrollton-area stores by Nov 30, 2026 (Assistant (draft) / Aslam (submit)) |
| 11 | Kroger Zero Hunger / Zero Waste Foundation + Kroger store giving zerohungerzerowastefoundation.org | Meals | Hunger relief, mobile pantries, food access; stores also give cash/gift cards/product. Watch: Kroger Dallas Division store requests go through the Kroger proposal portal (thekrogerco.versaic.com) | Unverified | Applications reviewed quarterly (exact 2026-27 dates Unverified) | Verified | Submit one request in Dec 2026 (Assistant (draft) / Aslam) |
| 12 | Albertsons Companies Foundation / Nourishing Neighbors (Tom Thumb, Albertsons) nourishingneighbors.com | Meals | Hunger relief; Innovation Incubation Fund for new food-security ideas. Watch: Must serve communities with an Albertsons-family store (Tom Thumb is in DFW); a local Tom Thumb in-kind/gift-card process is Unverified | Unverified | Rolling; reviewed monthly (per Nourishing Neighbors RFP page) | Verified | Check current open RFP; ask local Tom Thumb manager about product donations (Assistant / Volunteer) |
| 13 | H-E-B My Community Investment (H-E-B, Central Market, Joe V's) newsroom.heb.com | Meals, events | Hunger relief, community; not operating expenses or third-party fundraisers. Watch: H-E-B has opened stores in DFW (Plano, Frisco, Irving etc.) and has announced a Carrollton store; one request per event | Under $200 in store; larger online | Apply 8+ weeks before decision needed; re-apply yearly | Verified | Request food/gift cards for Community Dinner (apply by Mar 2027) (Assistant (draft) / Aslam) |
| 14 | Sprouts Healthy Communities Foundation - Neighborhood Grants sprouts.com | Meals, Maa's Place | Nutrition security, adult wellness, children's nutrition education. Watch: Healthy Communities ($50k-$100k) is invitation-only after a Neighborhood Grant | Up to $5,000 | 2026 window closed Jun 1; 2027 window not announced (Unverified) | Verified | Watch for spring 2027 window (Assistant) |
| 15 | Costco local warehouse donation costco.com | Meals | Children, education, health & human services; monetary requests via printed form at warehouse. Watch: Amounts not stated on official page | Small; exact amounts Unverified | 4-6 weeks ahead; one request per fiscal year (Sep-Aug) | Verified | Drop off form at nearest warehouse (Volunteer) (Volunteer) |
| 16 | Texas Instruments Foundation ti.com | All | Greater Dallas; human services among priorities; mostly by invitation. Watch: Unsolicited proposals generally not considered | Unverified | No open cycle; introduce via giving@ti.com | Verified | Aslam decides whether to send intro email (Aslam) |
| 17 | Toyota Motor North America / Toyota USA Foundation (Plano) toyotaeffect.com | All | Community grants by invitation only (invitation code). Watch: No unsolicited applications | Unverified | Invitation only | Verified | Build relationship via Toyota employee volunteers (Aslam) |
| 18 | AT&T Foundation + AT&T employee giving giving.att.com | All | Foundation is invitation only; employee gifts matched 1:1 up to $1,000/yr; volunteer grants. Watch: Match/volunteer grant figures from AT&T sustainability page (via search) | Up to $1,000 per employee | Anytime (employee-initiated) | Verified | Ask donors/volunteers who work at AT&T to submit matches (Staff) |
| 19 | Chipotle Community Fundraisers community.chipotle.com | Meals | 25% of qualifying sales from a fundraiser night (min. $150 sales). Watch: Local partner restaurants (Al Markaz, Popeyes franchise, Chef Chen) are better first choices | Typically a few hundred $ per night | 2026 applications closed; reopen March 2027 | Verified | Apply Mar 2027 (Volunteer) |
| 20 | City of Carrollton CDBG - Social/Public Services cityofcarrollton.com | Meals, Maa's Place | HUD CDBG for low-to-moderate income Carrollton residents; public services capped at 15% (~$113,000). Watch: Competitive; must document Carrollton low/mod-income clients | Pool ~$113,000 (PY2026 went entirely to Metrocrest Services) | PY2026: apps Mar 19-May 1, 2026. PY2027 dates not posted - expect spring 2027 (Unverified) | Verified | Call Community Development (972-466-4299) in Feb 2027 - Aslam (Aslam / Assistant) |
| 21 | North Texas Food Bank - Partner Agency (incl. TEFAP & senior programs) ntfb.org | Meals, Maa's Place | Low-cost/free food, USDA TEFAP commodities, produce; CSFP senior boxes distributed by NTFB. Watch: Clients in Dallas, Collin (and 10 other) counties - NOT Denton; needs food storage, food-safety rules | In-kind (could cut food cost substantially) | Applications reviewed quarterly: Jan, Apr, Jul, Oct | Verified | Confirm county of sites/clients; apply for Jan 2027 review (Aslam / Staff) |
| 22 | Tarrant Area Food Bank - Partner Agency (TAFB North serves Denton County) tafb.org | Meals | Partner agencies in 13 counties incl. Denton; meal programs need health permits. Watch: Must serve 6+ months; shared maintenance fees; monthly reports | In-kind | Rolling (submit prospective partner form) | Verified | Use only if clients/site are in Denton County (Staff) |
| 23 | Dallas Area Agency on Aging (Community Council of Greater Dallas) ccadvance.org | Maa's Place, Meals (seniors) | Older Americans Act Title III services for Dallas County 60+ via subrecipients. Watch: Title III providers must meet state AAA rules; realistic year-1 step is partnership/referrals | Unverified | No open RFP found (Unverified) | Verified | Request intro meeting (Aslam's decision) (Aslam) |
| 24 | North Central Texas Area Agency on Aging (NCTCOG) - Denton & Collin nctcog.org | Maa's Place, Meals (seniors) | 14-county AAA; Denton County meals provider is SPAN, Inc.; Collin is Meals on Wheels of Collin County. Watch: Funding goes to contracted providers; partnership/referral more realistic in year 1 | Unverified | No open RFP found (Unverified) | Verified | Ask about referrals to Maa's Place (Aslam) |
| 25 | Texas HHS - Area Agency on Aging nutrition rules (Title III pass-through) hhs.texas.gov | Seniors | State oversight of AAA nutrition programs (not a direct grant). Watch: No direct application; money flows through AAAs | n/a | n/a | Verified | Reference only (Assistant) |
| 26 | Rotary Club of Carrollton-Farmers Branch cfbrotary5810.org | All | Annual community-service grants to local nonprofits (e.g., Metrocrest Services, senior services). Watch: Application process/size not posted | Unverified | Unverified (annual) | Verified | Ask to present at a meeting; volunteers join a Saturday shift (Aslam) |
| 27 | Carrollton-area Lions Club(s) (no official page found) | All | Service projects (vision, youth). Watch: No official grant page found | Unverified | Unverified | Unverified | Ask a member contact; low priority (Volunteer) |
| 28 | Faith communities (mosques, temples, churches, gurdwaras in DFW) (no official page found) | All | Ramadan, Diwali, Thanksgiving and year-end drives; volunteer teams; in-kind. Watch: Partner names to come from Aslam; keep public posts non-religious | $1k-$15k per partner drive (estimate) | Ramadan ~Feb 8-Mar 9, 2027 (moon-sighting); Diwali Nov 8, 2026 | Unverified | Aslam lists 10 partners; Assistant drafts asks (Aslam) |
| 29 | Donor-advised funds (Fidelity Charitable, Schwab, CFT, NPT etc.) (no official page found) | All | Donors recommend grants from their DAF; needs our legal name + EIN on the website. Watch: Specific DAF-button tools/pricing not checked | Varies | Peak Nov-Dec | Unverified | Add 'Give from your DAF' text (EIN 86-2221897) to donate page (Assistant) |
| 30 | United Way of Denton County - Community Impact Grants unitedwaydenton.org | Low fit | Youth, workforce, veterans, homelessness, behavioral health. Watch: Focus areas do not match hunger/seniors well | Unverified | Unverified | Verified | Low priority (Assistant (track)) |

Important county question. Carrollton spans Dallas, Denton, and Collin counties. Whether each site and most clients are in Dallas or Denton County decides which food bank (NTFB or TAFB), which Area Agency on Aging (Dallas AAA or NCTCOG), and whether the Dallas Foundation is open to you (over 50% of clients must live in Dallas County). Aslam: please confirm (see Questions).

## 2(c) Corporate giving: what to ask for

| Type | What it is | Who to ask (DFW) | Owner |
| --- | --- | --- | --- |
| Community grants | Small cash grants from local stores | Walmart, Kroger, Tom Thumb/Albertsons, H-E-B, Sprouts, Costco | Assistant drafts / Aslam submits |
| Sponsorships | A business pays for visibility at an event or campaign | Restaurants, banks, realtors, clinics, car dealers near Carrollton | Aslam |
| Matching gifts | Employers match employee gifts (AT&T matches 1:1 up to $1,000 per employee per year) | Ask every donor: "Does your employer match?" | Staff |
| Dollars for doers | Employers give money when employees volunteer (AT&T has volunteer grants) | Ask the Saturday volunteers where they work | Staff |
| In-kind | Food, supplies, gift cards, delivery help | Grocers, distributors (Texas Wholesale already helps), restaurants | Volunteer / Aslam |

Sponsor tiers (draft; amounts for Aslam to set):

| Tier | Amount | Meals funded | Recognition |
| --- | --- | --- | --- |
| Meal Friend | $500 | 100 | Website partner list + thank-you post |
| Saturday Sponsor | $1,100 | 220 (a tenth of a Saturday) | + a mention in the weekly video |
| Senior Champion | $2,500 | 500 | + logo on the volunteer T-shirt / banner |
| Maa's Table | $5,000+ | 1,000+ | + Community Dinner table + logo on Maa's Place wall |

Steps: 1) Aslam approves the tiers. 2) Assistant makes a one-page sponsor sheet. 3) Aslam lists 20 businesses he knows. 4) Aslam makes the calls or visits (no outreach until he approves). 5) Staff logs each ask in the tracker.

## 2(d) Government and food programs (realistic view)

| Program | How it reaches you | Realistic in year 1? | Next step |
| --- | --- | --- | --- |
| USDA TEFAP commodities | Through a food bank partnership (NTFB lists TEFAP as a partner benefit) | Yes, after NTFB or TAFB approval | Apply for the Jan 2027 NTFB review |
| CSFP senior food boxes (60+) | Run by Texas Dept. of Agriculture with NTFB in Dallas County | Maybe, as a distribution site for Maa's Place seniors (Unverified) | Ask NTFB senior programs team |
| Older Americans Act Title III (meals, senior centers) | Through the Dallas AAA (Community Council of Greater Dallas) or NCTCOG AAA (Denton/Collin) to contracted providers | Unlikely as funding in year 1; good for referrals and partnership | Intro meeting (Aslam decides) |
| City of Carrollton CDBG public services | Yearly application, about $113,000 pool | Possible but competitive (all of PY2026 went to Metrocrest Services) | Watch for spring 2027 notice; call 972-466-4299 |
| Texas HHS | Oversees AAA nutrition rules; no direct grant | No | Reference only |

# 3. Existing Donors

## 3(a) Segments and how to treat each

| Segment | Definition | Main touch | Frequency | Owner |
| --- | --- | --- | --- | --- |
| New one-time | First gift in last 90 days | 48-hr thank-you + 90-day welcome series | Per schedule (Section 4) | Staff / Assistant |
| Repeat one-time | 2+ gifts, not monthly | Impact updates + monthly upgrade ask | Monthly email; 2 asks a year | Assistant / Aslam |
| Monthly (Maa's Circle) | Active recurring gift | Monthly video update; yearly thank-you call | Monthly | Assistant / Volunteer callers |
| Major | $1,000+ in 12 months [set threshold] | Personal: calls, handwritten notes, visits, tours | Quarterly in person or by phone | Aslam |
| Lapsed | Gave before, nothing in 13+ months | Win-back letter + call | Twice a year | Staff / Aslam |
| In-kind | Gave food or supplies | Thank-you with item description (no value) + photo of the food in use | After each gift | Staff |
| Corporate / partner | Business, restaurant, or grocer | Recognition, impact report, renewal meeting | Quarterly | Aslam |
| Volunteers who also give | Both | Volunteer + donor thank-you; peer-to-peer invite | Quarterly | Staff |

## 3(b) Data to track for every donor

Name · household/organization · email · phone · mailing address · preferred contact (email/text/call/mail) · language (English, Urdu/Hindi, Gujarati, other) · first gift date/amount · last gift date/amount · total given (lifetime, this year) · number of gifts · gift type (Stripe one-time, Stripe monthly, check, cash, in-kind, DAF, matching gift, grant) · program (Meals, Maa's Place, BSV, general, taken from Stripe client_reference_id) · campaign/appeal · tribute (in honor/memory of) · employer (for matching) · acknowledgment sent (date, who) · goods/services given (for quid pro quo) · in-kind description · volunteer (yes/no) · relationship owner · notes · do-not-contact / anonymous flags · photo consent on file (yes/no).

## 3(c) Donor database (CRM): recommendation

| Tool | Price (checked Oct 13, 2026) | Works with our Stripe links? | Good for | Watch out |
| --- | --- | --- | --- | --- |
| Little Green Light (recommended) | $45/mo up to 2,500 records; unlimited users; 10% off annual | Yes: Stripe through LGL Forms, or a Stripe-to-LGL Zapier connection | Small teams, mail merge letters, year-end statements, segments | Separate tool from the donation page |
| Zeffy | Free (paid for by optional donor tips) | Uses its own payment pages (would replace or sit beside Stripe links) | Zero cost, events, raffles, peer-to-peer | Donors see a tip prompt; moving off Stripe changes the giving process |
| Givebutter | Free with optional tips; 3% fee if tips are off; Plus from $29/mo | Uses its own checkout; Stripe data by CSV import | Peer-to-peer, events, texting | Same tip prompt trade-off |
| Bloomerang | From $125/mo (billed annually) | Has its own giving forms | Strong retention reports | Costs more than we need now |
| DonorPerfect | Core about $99 to $119/mo (sources differ; Unverified) | Has its own forms | Larger shops | Costs more than we need now |

Recommendation: Use Little Green Light now and keep the current Stripe donation process. If cost must be $0, use Zeffy or Givebutter's free CRM and import Stripe each month. QuickBooks (from the earlier finance plan) stays the accounting record. The CRM is the relationship record. Reconcile the two each month.

How to connect Stripe and other records (steps):

1.  Aslam creates the LGL account and adds Staff and Assistant as users.

2.  Import past donors: Stripe export (Payments > Export, all of 2025 and 2026), plus the check/cash ledger and in-kind list.

3.  Turn on one ongoing link: either a Zapier zap (Stripe "new payment" creates an LGL gift) or a weekly Stripe CSV import. The Stripe client_reference_id (meals / maas-place / bsv / general) maps to the LGL "Fund."

4.  Checks and cash are entered from the two-person count sheet (same as the finance plan). In-kind gifts are entered with a description and no value in the letter.

5.  Monthly: Stripe payouts are matched to the bank in QuickBooks, LGL gift totals are matched to QuickBooks income, and any differences are fixed.

## 3(d) Outreach plan by group

| Group | Email | Text | Call | Handwritten note | Visit / tour |
| --- | --- | --- | --- | --- | --- |
| New donor | Within 48 hrs + day 7, 30 | Optional thank-you text if they gave a phone | If $250+ | If $100+ | Invite at day 60 |
| Monthly | Monthly video update | Birthday/anniversary text | Once a year (volunteer caller) | Once a year | Open invitation |
| Major | Quarterly personal update | As preferred | Aslam, quarterly | After every gift | Twice a year |
| Lapsed | Win-back letter (template) | One friendly text | One call | No | Invite to a Saturday |
| In-kind / partner | Thank-you + photo | As preferred | After big drops | Yearly | Yearly recognition |
| Corporate | Quarterly impact report | No | Renewal call | Yearly | Yearly site visit |

## 3(e) Draft templates (DRAFTS ONLY: nothing is sent without Aslam's approval)

Template 1: Thank-you letter (all gifts; send within 48 hours)

Dear [First Name], Thank you. Your gift of $[amount] on [date] will put [amount ÷ 5] hot meals into the hands of seniors and neighbors in need across Dallas-Fort Worth. Every Saturday, about 50 volunteers cook, pack, and deliver about 2,200 fresh meals from our kitchen in Carrollton. More than 120 senior families count on that knock at the door. Your gift is part of every one of those meals. We started Maa's Inspiration in memory of our mother, Gulbano. We called her Maa. Her greatest joy was feeding others, and no one ever left her home hungry. Thank you for carrying that spirit forward with us. [Choose one: No goods or services were provided in exchange for this contribution. / You received [description], with an estimated value of $[value]; the tax-deductible portion of your gift is $[amount minus value].] Maa's Inspiration Inc. is a 501(c)(3) nonprofit, EIN 86-2221897. Please keep this letter for your tax records. With gratitude, Aslam Hemani, Director · aslam@maasinspiration.org · 214-517-1938 P.S. Come see it for yourself any Saturday, 10 AM to noon, at 1445 MacArthur Dr Suite 104, Carrollton.

Template 2: Impact update (email; monthly or quarterly)

Subject: What your meals did this month Hi [First Name], This month, you helped us serve [#] hot meals over [#] Saturdays, including [#] meals delivered to senior families. [#] volunteers gave [#] hours. [One short story, first name only and with consent: e.g., "Mrs. [first name], 78, told our driver the meal is the only hot food she has all week."] Coming up: [Maa's Place opening date / next Saturday event]. [Watch the 30-second video] · [Give a meal: $5] Thank you for being part of this. Love All, Serve All. Aslam

Template 3: Appeal letter (year-end or campaign)

Dear [First Name], Every Saturday morning, our volunteers pack about 2,200 hot meals. By noon, they are at the doors of seniors, at shelter homes, and in the hands of neighbors who would otherwise go without. It costs about $5 to make and deliver one meal. 100% of donations fund meals. We pay no salaries. This [season / month], will you help us keep every Saturday full? • $25 feeds a senior family for a week • $100 covers a full delivery run for 20 people • $500 funds 100 hot meals Give at maasinspiration.org/donate.html, or mail a check to Maa's Inspiration Inc., [mailing address]. [If there is a match: "Thanks to [sponsor], every gift through [date] is doubled up to $[X]."] With gratitude, Aslam Hemani, Director P.S. A monthly gift of $25 feeds a senior family every week of the year. You can join Maa's Circle on the same page.

Template 4: Monthly giving upgrade ask (for repeat one-time donors)

Subject: Could you feed a senior every week? Hi [First Name], You have given [#] times. Thank you. Here is one small change that would mean a lot: join Maa's Circle with a monthly gift. $25 a month = 5 hot meals every month, without you having to remember. You can change or cancel anytime. [Join Maa's Circle] (link to donate.html with Monthly selected) Members get a 60-second video every month showing exactly what their gift did. Thank you, Aslam

Template 5: Lapsed donor win-back

Subject: We miss you at the table Hi [First Name], You helped us serve meals back in [year]. Thank you. Since then, a lot has grown: we now serve about 2,200 meals every Saturday, and we are opening Maa's Place, a free senior center in Carrollton. We would love to have you back, in whatever way fits: a gift of any size, a Saturday volunteer shift, or just a visit to see the kitchen. [Give a meal: $5] · [Volunteer on a Saturday] If you'd rather not hear from us, just reply and we'll update our list. With thanks, Aslam

Template 6: Year-end giving statement (send by Fri Jan 29, 2027)

Maa's Inspiration Inc. · 501(c)(3) · EIN 86-2221897 · [mailing address] · aslam@maasinspiration.org [Year] Giving Statement for [Donor Name], [Address] Date; Amount; Method; Program; Goods or services received. [MM/DD]; $[ ]; [Stripe / check # / cash]; [Meals]; None. [MM/DD]; $[ ]; [ ]; [ ]; [Dinner ticket: value $[ ]; deductible $[ ]]. Total; $[ ]. Unless noted above, no goods or services were provided in exchange for these contributions. In-kind gifts are listed by description only; Maa's Inspiration does not assign them a value. Please keep this statement for your tax records. Thank you for feeding our neighbors this year. Aslam Hemani, Director

Template 7 (optional): Business sponsor note (for Aslam to use only after he approves)

Hi [Name], thank you for [what they already do]. We feed about 2,200 people every Saturday in Carrollton. Would [Business] sponsor a tenth of one Saturday ($1,100 = 220 meals)? We'd thank you on our website and in our weekly video. Happy to show you the kitchen any Saturday. Aslam, 214-517-1938

# 4. Follow-Up and Processes

## 4(a) Thank-you rules by gift size

| Gift | Within 48 hours | Within 7 days | Extra |
| --- | --- | --- | --- |
| Under $100 | Email thank-you (Template 1) | — | Added to impact updates |
| $100 to $249 | Email thank-you | Handwritten note (Volunteer writes, Aslam signs) | — |
| $250 to $999 | Aslam calls or texts + formal letter with IRS wording | Handwritten note | Tour invite |
| $1,000+ | Aslam calls the same or next day | Letter + note | Visit or coffee within 30 days |
| Monthly (new) | Welcome email + video | Welcome call (Volunteer) | Monthly update |
| In-kind | Thank-you with item description (no value) | Photo of items in use | — |
| Grant | Thank-you to program officer | Add report dates to grant calendar | — |

## 4(b) IRS-compliant acknowledgments (Texas nonprofits follow the federal rules)

| Rule | What we must do | Template |
| --- | --- | --- |
| Gift of $250 or more (single gift) | Written acknowledgment showing org name, amount (or item description), and whether goods or services were given. The donor needs it before filing. | Template 1 with the IRS line |
| Quid pro quo payment over $75 (e.g., dinner ticket) | Written disclosure: the deductible amount is the payment minus the fair market value of what they got, with a good-faith estimate of that value. Print it on tickets and receipts. | Finance plan Template B |
| In-kind gifts | Describe the items (e.g., "40 cases of canned vegetables"). Do not state a value. Valuing it is the donor's job. | Finance plan Template C |
| Year-end statement | Every gift for the year with goods/services wording | Template 6 (send by Jan 29) |
| Raffle tickets | Not deductible (the buyer gets a chance to win) | Print "not tax-deductible" on tickets |

Source: IRS Publication 1771 and the IRS written-acknowledgment page (links in the appendix). The CPA should review the templates once before first use.

## 4(c) 90-day follow-up after every gift

| Day | Touch | Channel | Owner |
| --- | --- | --- | --- |
| 0 to 2 | Thank you (call if $250+) | Email / text / call | Staff / Aslam |
| 7 | Welcome + 30-second video of a Saturday | Email | Assistant (drafts), Staff sends after approval |
| 30 | Impact update (what their gift did) | Email (or mail for check donors) | Assistant / Staff |
| 60 | Invitation: visit on Saturday, volunteer, Maa's Place tour | Email / text | Staff |
| 90 | Short 3-question survey ("Why did you give?") or, for engaged donors, the monthly upgrade ask | Email | Assistant / Aslam |

## 4(d) Ongoing yearly touch schedule (every donor gets about 2 asks for every 5 non-ask touches)

| Month | Touch |
| --- | --- |
| Jan | Year-end statement + thank-you · Founding Friends (Maa's Place) |
| Feb | Impact update #1 · Ramadan "Share a Meal" (partners) |
| Mar | Maa's Place opening invitation |
| Apr | Volunteer appreciation story · Maa's Day starts |
| May | Maa's Day ask + Community Dinner |
| Jun | Mid-year impact update (no ask) |
| Jul | Summer senior appeal |
| Aug | Monthly upgrade ask · NTxGD heads-up |
| Sep | North Texas Giving Day ask |
| Oct | Annual impact report (no ask) |
| Nov | Thanksgiving thank-you (no ask) · Diwali/Thanksgiving "Share a Plate" for partners |
| Dec | Giving Tuesday + year-end appeal |

## 4(e) Grant management process

1.  Find (Assistant): keep the Funders tab current. Check deadlines on the 1st of each month.

2.  Decide (Aslam): go/no-go within 1 week of a match. Ask: do we fit, and is the effort worth the likely award?

3.  Prepare (Assistant): keep a ready folder with the IRS determination letter, latest Form 990, budget (and budget vs. actual), board list, financial statements/audit status, W-9, program numbers, photos (consent on file), and 3 short stories.

4.  Draft (Assistant), review and submit (Aslam). Aim to finish 5 business days before the deadline.

5.  Track (Staff): status in the Funders tab: Researching / Drafting / Submitted / Awarded / Declined / Report due.

6.  Award (Aslam): sign the agreement. Put every report date and restriction in the calendar on the same day. Tag spending in QuickBooks by grant.

7.  Report (Assistant drafts, Aslam approves): send 2 weeks before the due date, with numbers, a story, and photos.

8.  Renew (Aslam): thank the funder 3 times a year. Ask about renewal 3 months before the grant ends.

9.  Declined? Ask for feedback politely and note when you can reapply.

## 4(f) Who does what

| Task | Aslam | Staff | Volunteer | Assistant |
| --- | --- | --- | --- | --- |
| Approve all letters, posts, and asks | ✔ |  |  |  |
| Personal calls ($250+, major, sponsors) | ✔ |  |  |  |
| Log gifts in CRM, 48-hr thank-you emails |  | ✔ |  | drafts |
| Handwritten notes | signs |  | ✔ |  |
| Monthly impact numbers (meals, volunteers) |  | ✔ |  | formats |
| Grant research, drafts, reports | submits | tracks |  | ✔ |
| Event logistics | decides | ✔ | ✔ | checklists |
| Monthly metrics report | reviews |  |  | ✔ |
| Year-end statements | signs | checks |  | ✔ |

## 4(g) Weekly checklist (Monday, 30 minutes)

☐  All gifts from last week entered in the CRM (Stripe, checks, cash, in-kind) (Staff)

☐  Every gift thanked within 48 hours; $250+ have the IRS wording (Staff)

☐  Aslam has called all $250+ donors from last week (Aslam)

☐  Handwritten notes written and mailed (Volunteer)

☐  Saturday numbers recorded: meals, volunteers, senior families (Staff)

☐  Next 30 days of grant deadlines checked (Assistant)

☐  Campaign of the month on track; social Post 3 shows the current ask (Assistant)

☐  New volunteer/donor photo consents logged (Staff)

## 4(h) Monthly checklist (by the 10th)

☐  CRM totals match QuickBooks; Stripe payouts match the bank (Staff / Aslam)

☐  Metrics report: retention, average gift, monthly donors, cost per dollar raised (Assistant)

☐  Impact update email sent (Assistant drafts, Aslam approves)

☐  Lapsed donors (13+ months) list pulled; win-back steps assigned (Staff)

☐  Grant calendar and reports reviewed (Assistant / Aslam)

☐  Sponsor recognition posted (website/video) (Assistant)

☐  Next month's campaign materials approved (Aslam)

# 5. Everything Else

## 5(a) 12-month goals

| Goal | Target by Oct 31, 2027 | Starting point |
| --- | --- | --- |
| Total raised (all sources) | [12-month goal $] (planning range $86,500 to $405,500) | Last year: [$] |
| Monthly donors (Maa's Circle) | 100 [confirm] | [#] today |
| Monthly recurring revenue | $3,000/month [confirm] | [$] |
| Donor retention | 50%+ | [%] |
| Thank-yous within 48 hours | 95%+ | — |
| Grants submitted / won | 10 submitted / 4 won | [#] |
| Business sponsors | 15 | [#] |
| Cost per dollar raised | Under $0.20 | — |
| Maa's Place opening campaign | 100% of opening costs + 3 months of running costs | [$] |

## 5(b) Budget with placeholders

Maa's Place and Blooming Star Village (Aslam to fill in)

| Item | Maa's Place: one-time | Maa's Place: monthly | BSV: one-time | BSV: monthly |
| --- | --- | --- | --- | --- |
| Lease deposit / rent | [$] | [$] | [$] (shared space?) | [$] |
| Build-out, accessibility, safety (ramps, grab bars, sensory room) | [$] | — | [$] | — |
| Furniture, chairs, tables | [$] | — | [$] | — |
| Kitchen / snack and chai equipment | [$] | — | [$] | — |
| Activity and sensory supplies | [$] | [$] | [$] | [$] |
| Snacks, chai, fruit | — | [$] | — | [$] |
| Utilities, internet, phone | — | [$] | — | [$] |
| Insurance (general liability, D&O, accident; abuse & molestation for BSV) | [$] | [$] | [$] | [$] |
| Background checks, training, first aid/CPR | [$] | [$] | [$] | [$] |
| Licensing or exemption costs (BSV: check Texas child-care rules) | — | — | [$] | [$] |
| Coordinator / specialist staff (if any; see the "no salaries" question) | — | [$] | — | [$] |
| Cleaning, maintenance | — | [$] | — | [$] |
| Signage, printing | [$] | [$] | [$] | [$] |
| Total | [$] | [$] | [$] | [$] |

Fundraising costs (12 months, estimates)

| Item | Estimate |
| --- | --- |
| Little Green Light CRM ($45/mo) | $540 |
| Printing and postage (2 mailed appeals, year-end statements, notes) | $1,500 to $3,000 |
| Community Dinner (venue, food, A/V; offset by sponsors) | $5,000 to $15,000 |
| Maa's Place opening event | $500 to $2,000 |
| Sponsor kit, banners, signs | $300 to $800 |
| North Texas Giving Day (CFT covers card fees) | $0 to $300 |
| Stripe fees (2.2% + 30¢ if the nonprofit rate is approved; otherwise standard) | [% of online gifts] |
| Total | about $7,800 to $21,600 + Stripe fees |

The workbook's Budget tab has these lines with formulas.

## 5(c) Board and volunteer roles

Board (names: [Board members]). Suggested minimum: 3 to 5 people (confirm what your bylaws require).

Every board member: gives a personal gift each year at a level meaningful to them, opens 3 doors (introductions) a year, and attends the Community Dinner.

Board Chair: runs meetings and partners with Aslam.

Treasurer: reviews the monthly report and reconciliation (not the person entering gifts).

Fundraising chair: leads the sponsor and dinner committees.

Secretary: minutes and policies (privacy, gift acceptance, conflict of interest).

Volunteer fundraising roles

| Role | Time | What they do |
| --- | --- | --- |
| Thank-you caller | 1 hr/week | Calls new and monthly donors to say thanks (no asking) |
| Note writer | 1 hr/week | Handwritten notes for $100+ gifts |
| Event lead | 4 hrs/week (Mar to May) | Runs Community Dinner logistics |
| Peer-to-peer captain | 2 hrs/month | Recruits 5 friends to fundraise (NTxGD, birthdays) |
| Grant helper | 2 hrs/week | Finds numbers and photos for applications |
| Story & photo volunteer | Saturdays | Captures photos/video with consent forms, logs them |
| Data volunteer | 2 hrs/week | Enters checks, cash, and in-kind into the CRM (not the person who counted the cash) |

## 5(d) Storytelling (consistent with the social media plan)

Social stays on TikTok, Instagram @maasinspiration, and Facebook (facebook.com/maasinspiration) only. No X.

Use the existing 4-videos-per-week program (launch week Oct 26, 2026). Post 3 (Donation Impact) carries the campaign of the month. The donation QR stays on screen for the full 30 seconds.

Use only your own footage. No identifiable senior, child, or volunteer without a signed consent form on file. For Blooming Star Village, use a parent/guardian consent; avoid faces of children unless it is truly needed; never use last names or health details.

No politics or religion in public posts. Faith partners can promote campaigns in their own channels.

Story bank: every Saturday, Staff writes down one short story (first name only, with consent) and one number. The Assistant turns them into the impact update, Post 3, and grant reports.

Every link carries the program tag (donate.html?program=meals, ?program=maas-place, ?program=bsv) so you can see which story raised money.

## 5(e) Rules: raffles, events, donor privacy (Texas + IRS)

Texas Charitable Raffle Enabling Act (Occupations Code Ch. 2002). Verified with the Texas Attorney General.

| Rule | Detail |
| --- | --- |
| Who | A 501(c) nonprofit that has existed at least 3 years (Maa's Inspiration likely qualifies at 5+ years; confirm the incorporation date) |
| How many | Up to 4 raffles per calendar year. The brief said 2; the law changed from 2 to 4 in June 2021 (HB 2757). |
| Prizes | No cash prizes (prepaid gift cards are allowed). A purchased prize can be worth up to $75,000. Donated prizes have no limit. You must own the prize or post a bond before the drawing. |
| Selling | No statewide promotion or ticket sales. The AG says this is generally read to include online sales, so sell paper tickets in person. You can mention it on your own website and to existing supporters. |
| People | No paid organizers or ticket sellers (volunteers only) |
| Ticket must show | Org name · org (or officer) address · ticket price · description of each prize over $10 · drawing date |
| Not allowed | Casino nights and poker nights (no nonprofit exception in Texas) |
| IRS | Tickets are not deductible. A W-2G is required if the prize minus the ticket price is at least $2,000 (2026 threshold) and at least 300 times the ticket price. Withhold 24% if it is over $5,000. Confirm with the CPA. |

Events

Print the quid pro quo disclosure on dinner tickets: "$[price] ticket includes dinner valued at $[value]; $[difference] is tax-deductible."

Texas sales tax: a qualifying 501(c)(3) can hold two one-day tax-free sales or auctions per calendar year. This needs Texas exemption status (Form AP-204). Confirm you have it.

Alcohol, food permits, venue insurance: confirm with the venue and city (Unverified here; most community dinners are alcohol-free, which keeps it simple).

Donor privacy

Adopt a one-paragraph donor privacy policy: "We never sell, rent, or share donor information." Put it on the donate page.

Keep donor data in the CRM (not personal Gmail or phones). Give access only to people who need it.

Card data stays with Stripe; never write card numbers down.

Honor "anonymous" and "do not contact" flags. Don't name donors publicly without permission.

Form 990 Schedule B donor names are not part of the public copy for 501(c)(3)s. Still, treat the list as confidential.

## 5(f) Key metrics (tracked monthly in the workbook)

| Metric | Formula | Target |
| --- | --- | --- |
| Donor retention | Donors who gave last year AND this year ÷ donors last year | 50%+ |
| New donor retention | First-time donors who give again within 12 months ÷ first-time donors | 35%+ |
| Average gift | Total $ ÷ number of gifts | Track; rise over time |
| Monthly donors | Active recurring donors at month end | 100 by Oct 2027 |
| Monthly recurring revenue | Sum of active monthly gifts | $3,000/mo |
| Cost per dollar raised | Fundraising costs ÷ dollars raised | Under $0.20 |
| 48-hour thank-you rate | Gifts thanked within 48 hrs ÷ all gifts | 95%+ |
| Lapsed reactivated | Lapsed donors who gave again | 10% of lapsed |
| Grant win rate | Grants won ÷ submitted | 30% to 40% |
| Cost per meal | Meal costs ÷ meals served | about $5 (confirm) |

# 12-Month Fundraising Calendar (Nov 2026 to Oct 2027)

Why this window: it starts right after the social media launch (Oct 26) and the finance go-live (Nov 2). It catches Giving Tuesday and year-end, when most giving happens, and it ends after North Texas Giving Day, so year two can be planned with real numbers.

| Month | Theme | Key dates | Campaigns | Grants | Donor care |
| --- | --- | --- | --- | --- | --- |
| Nov 2026 | Get ready + first asks | Nov 2 NTxGD reg. opens; Nov 8 Diwali; Nov 26 Thanksgiving; Nov 30 Walmart deadline | Maa's Circle launch; Share a Plate | Walmart; CFT profile | Set up CRM; 48-hr thank-yous start |
| Dec 2026 | Year-end giving | Dec 1 Giving Tuesday; Dec 31 tax year ends | Giving Tuesday; year-end appeal | Kroger; Albertsons | Holiday cards to top 50 donors |
| Jan 2027 | Thank + build | Jan 29 year-end statements | Founding Friends (Maa's Place) | NTFB (Jan review); Moody; Meadows | Thank-a-thon calls |
| Feb 2027 | Ramadan season | ~Feb 8 Ramadan begins; Feb 15 Hoblitzelle window opens | Share a Meal (faith partners); sponsor tiers | Walmart cycle 1 (if repeated) | Impact update #1 |
| Mar 2027 | Maa's Place opens [TBA] | ~Mar 9-10 Eid al-Fitr; Chipotle reopens | Opening event; Founding Friends close | Carrollton CDBG (if open); H-E-B | Tour invites for $250+ donors |
| Apr 2027 | Dinner prep | Apr 19 Maa's Day campaign starts | Dinner sponsors + tickets | Kroger quarterly | Volunteer appreciation |
| May 2027 | Maa's Day | May 9 Mother's Day | Maa's Day tributes; Community Dinner | - | Dinner thank-yous in 48 hrs |
| Jun 2027 | Mid-year | Hoblitzelle 2nd window Jun 15 | Birthday fundraisers | Dallas Foundation summer (if open) | Mid-year impact update |
| Jul 2027 | Summer needs | - | Summer senior meals appeal | Sprouts (if open) | Monthly donor upgrade ask |
| Aug 2027 | Giving Day build | ~Late Aug NTxGD early giving | Peer-to-peer pages; match pool | Rees-Jones LOI (BSV, if dated) | Lapsed donor win-back |
| Sep 2027 | North Texas Giving Day | Sep 16 NTxGD | NTxGD push | - | Thank all NTxGD donors in 48 hrs |
| Oct 2027 | Review + plan year 2 | Diwali 2027 (date TBC) | Annual impact report | Renewals list | Donor survey |

# Master Action Table

Goal $ is a planning estimate. Status starts as "Not started"; update it in the workbook.

| Month | Activity | Owner | Goal $ | Status |
| --- | --- | --- | --- | --- |
| Nov 2026 | Fix donate page: real monthly links, custom amount link, program tags on Meals/BSV pages, IRS receipt text | Assistant (draft) / Aslam (approve) | - | Not started |
| Nov 2026 | Request Stripe nonprofit rate (2.2% + 30c) | Aslam | - | Not started |
| Nov 2026 | Set up donor database (Little Green Light) and import Stripe + check/cash records | Assistant / Staff | - | Not started |
| Nov 2026 | Launch Maa's Circle monthly giving (goal: 40 monthly donors by Dec 31) | Aslam / Assistant | $1,500 | Not started |
| Nov 2026 | Walmart Spark Good applications to 2-3 nearby stores (deadline Nov 30) | Assistant (draft) / Aslam (submit) | $5,000 | Not started |
| Nov 2026 | Register for North Texas Giving Day 2027 (opens Nov 2) | Assistant / Aslam | - | Not started |
| Nov 2026 | Complete CFT Nonprofit Gateway Profile | Assistant (draft) / Aslam | - | Not started |
| Nov 2026 | Diwali (Nov 8) + Thanksgiving (Nov 26) 'Share a Plate' with partner temples/businesses | Aslam / Volunteer | $6,000 | Not started |
| Nov 2026 | Recruit 3 board/fundraising committee members | Aslam | - | Not started |
| Dec 2026 | Giving Tuesday Dec 1 (match from 1-2 sponsors) | Aslam / Assistant | $8,000 | Not started |
| Dec 2026 | Year-end appeal: letter + 4 emails (Dec 1, 15, 29, 31) | Assistant (draft) / Aslam | $12,000 | Not started |
| Dec 2026 | Kroger + Albertsons/Nourishing Neighbors requests | Assistant (draft) / Aslam | $3,000 | Not started |
| Dec 2026 | Restaurant give-back night #1 (existing partner) | Volunteer | $800 | Not started |
| Jan 2027 | Year-end giving statements sent by Jan 29 | Assistant / Aslam | - | Not started |
| Jan 2027 | Thank-a-thon: call every $250+ and every monthly donor | Aslam / Volunteers | - | Not started |
| Jan 2027 | NTFB partner agency application (Jan quarterly review) | Aslam / Staff | - | Not started |
| Jan 2027 | Maa's Place 'Founding Friends' campaign kickoff | Aslam / Staff | $10,000 | Not started |
| Jan 2027 | Moody + Meadows inquiries for Maa's Place | Assistant (draft) / Aslam | - | Not started |
| Feb 2027 | Business sponsorship tiers sent to 20 local businesses (after approval) | Aslam | $15,000 | Not started |
| Feb 2027 | Ramadan 'Share a Meal' with mosques/community partners (~Feb 8-Mar 9) | Aslam | $20,000 | Not started |
| Feb 2027 | Restaurant give-back night #2 | Volunteer | $800 | Not started |
| Mar 2027 | Carrollton CDBG application (if open, spring 2027) | Assistant (draft) / Aslam | $10,000 | Not started |
| Mar 2027 | Maa's Place opening event + Founding Friends close [date TBA] | Aslam / Staff | $15,000 | Not started |
| Mar 2027 | Chipotle fundraiser application (reopens March) | Volunteer | - | Not started |
| Mar 2027 | H-E-B request for Community Dinner (8+ weeks ahead) | Assistant (draft) / Aslam | $1,000 | Not started |
| Apr 2027 | Community Dinner: venue, sponsors, tickets with quid pro quo disclosure | Aslam / Volunteer lead | - | Not started |
| Apr 2027 | Volunteer appreciation + peer-to-peer captains recruited | Staff | - | Not started |
| Apr 2027 | Restaurant give-back night #3 | Volunteer | $800 | Not started |
| May 2027 | Maa's Day tribute campaign (Apr 19-May 9) | Assistant / Aslam | $10,000 | Not started |
| May 2027 | Annual Community Dinner 'Love All, Serve All' (net) | Aslam / Volunteer lead | $30,000 | Not started |
| Jun 2027 | Dallas Foundation Summer cycle (if open) | Assistant (draft) / Aslam | $25,000 | Not started |
| Jun 2027 | Mid-year impact update to all donors | Assistant / Aslam | - | Not started |
| Jun 2027 | Restaurant give-back night #4 | Volunteer | $800 | Not started |
| Jul 2027 | Summer senior meals appeal (heat) | Assistant / Aslam | $5,000 | Not started |
| Jul 2027 | Secure NTxGD match pool from 2-3 sponsors | Aslam | $5,000 | Not started |
| Aug 2027 | NTxGD early giving opens (~late Aug); peer-to-peer pages live | Assistant / Volunteers | - | Not started |
| Aug 2027 | BSV 'Founding Families' case + Rees-Jones LOI (if opening date set) | Assistant (draft) / Aslam | - | Not started |
| Aug 2027 | Restaurant give-back night #5 | Volunteer | $800 | Not started |
| Sep 2027 | North Texas Giving Day Thu Sep 16 | Aslam / Assistant | $12,000 | Not started |
| Oct 2027 | 12-month review: metrics, donor retention, plan for year 2 | Aslam / Assistant | - | Not started |
| Oct 2027 | Annual impact report + Diwali 2027 drive | Assistant / Aslam | $3,000 | Not started |
| Oct 2027 | Restaurant give-back night #6 | Volunteer | $800 | Not started |
| Total |  |  | $201,300 |  |

# Questions for Aslam

1.  Numbers: What is the annual operating budget [$], the amount raised last year [$], and the number of donors [#]? What 12-month goal [$] do you want?

2.  Stripe: Are the 7 current Payment Links one-time or recurring? Who owns the Stripe account? May we apply for the nonprofit rate?

3.  Meal cost: Does "$5 per meal" include donated food? About how much of the Saturday food is bought vs. donated? (At $5, 2,200 meals is about $11,000 per Saturday.)

4.  The 100% claim: "100% of donations fund meals, no salaries" is confirmed for Maa's Meals. How should we word it for Maa's Place and BSV, which will have rent and other costs? Who covers costs like rent and Stripe fees today?

5.  Counties: Are 1445 MacArthur Dr and 2700 Old Denton Rd in Dallas or Denton County? Where do most clients live? (This decides NTFB vs. TAFB, Dallas AAA vs. NCTCOG, and Dallas Foundation eligibility.)

6.  Maa's Place opening date and opening budget? BSV opening date, staffing, and whether you have checked Texas child-care licensing rules for a day program for children 5 to 17 (Unverified here; check with Texas HHS Child Care Regulation)?

7.  Board: Who is on the board [names]? Is anyone willing to chair fundraising?

8.  Audit and 990: Do you have a recent Form 990 and financial statements? Any audit? (Needed for most foundations.)

9.  Texas sales-tax exemption: Has Maa's Inspiration filed Form AP-204 with the Texas Comptroller?

10.  Incorporation date (for the 3-year raffle rule)?

11.  Faith and community partners: Which 10 mosques, temples, churches, and community groups should be invited to partner?

12.  Businesses: Which 20 local businesses or restaurants should get the sponsor sheet, and may Aslam make those asks?

13.  Community Dinner: OK to plan for May 2027 (Maa's Day week)? Any venue in mind?

14.  Mailing address for checks, and which email should receive donor forms instead of the personal Gmail?

15.  Major gift level: Is $1,000 a year the right "major donor" line for you?

16.  Maa's memory: Is there a date (birthday or anniversary) you'd like to honor with a yearly "Maa's Day of Service"?

# Appendix: Verification Log (checked Oct 13, 2026)

Count: 51 items verified and 11 items unverified, across 30 funder entries and 32 facts/rules/prices. A funder marked Verified means the program, eligibility and link were confirmed on an official page. Award sizes or future dates may still be marked Unverified inside the entry.

| # | Item | Finding | Status | Source |
| --- | --- | --- | --- | --- |
| 1 | North Texas Giving Day 2026 date | Thu Sep 17, 2026 (already passed) | Verified | northtexasgivingday.org |
| 2 | North Texas Giving Day 2027 date | Thu Sep 16, 2027 | Verified | cftexas.org |
| 3 | NTxGD 2027 registration | Opens Nov 2, 2026 | Verified | northtexasgivingday.org |
| 4 | Giving Tuesday 2026 | Tue Dec 1, 2026 (day after Thanksgiving week; Thanksgiving Nov 26) | Verified | Calendar |
| 5 | Diwali 2026 | Sun Nov 8, 2026 | Verified | globalpanchang.com |
| 6 | Ramadan 2027 | Expected to start ~Mon Feb 8, 2027; Eid al-Fitr ~Mar 9-10 (moon-sighting) | Unverified | khaleejtimes.com |
| 7 | Mother's Day 2027 | Sun May 9, 2027 | Verified | Calendar |
| 8 | Texas raffles: who can hold them | 501(c) nonprofit in existence 3+ years (plus religious societies 10+ yrs, volunteer fire/EMS) | Verified | texasattorneygeneral.gov |
| 9 | Texas raffles: how many | Up to 4 per calendar year (changed from 2 in June 2021 by HB 2757) | Verified | texasattorneygeneral.gov |
| 10 | Texas raffles: prizes | No cash prizes; purchased prize max $75,000; donated prizes no limit; must own prize or post bond | Verified | statutes.capitol.texas.gov |
| 11 | Texas raffles: selling | No statewide promotion or ticket sales (generally read to include the internet); no paid organizers; 5 items on each ticket | Verified | texasattorneygeneral.gov |
| 12 | Casino/poker night fundraisers | Not allowed for nonprofits in Texas | Verified | texasattorneygeneral.gov |
| 13 | IRS raffle prize reporting | W-2G if prize minus ticket price is at least $2,000 (2026 threshold) and 300x the ticket; 24% withholding over $5,000 | Verified | irs.gov |
| 14 | IRS written acknowledgment | Needed for any single gift of $250+; must say whether goods/services were given | Verified | irs.gov |
| 15 | IRS quid pro quo disclosure | Required when a payment over $75 is partly a gift and partly goods/services | Verified | irs.gov |
| 16 | IRS Publication 1771 | Charity guide to substantiation and disclosure | Verified | irs.gov |
| 17 | Texas tax-free sales/auctions | Two one-day tax-free sales or auctions per calendar year (needs Texas exemption, Form AP-204) | Verified | comptroller.texas.gov |
| 18 | Stripe nonprofit rate | 2.2% + 30c for eligible 501(c)(3)s with 80%+ donation volume; request via Stripe support / nonprofit@stripe.com | Verified | support.stripe.com |
| 19 | Little Green Light price | $45/mo up to 2,500 records; unlimited users; 10% off annual | Verified | littlegreenlight.com |
| 20 | LGL + Stripe | LGL Forms accept Stripe; Zapier Stripe-to-LGL zaps exist | Verified | help.littlegreenlight.com |
| 21 | Bloomerang price | Starts at $125/mo billed annually | Verified | bloomerang.com |
| 22 | DonorPerfect price | Core plan from ~$99-$119/mo (sources differ) | Unverified | donorperfect.com |
| 23 | Givebutter price | Free with optional donor tips; 3% platform fee if tips off; Plus from $29/mo | Verified | givebutter.com |
| 24 | Zeffy price | Free to nonprofits (funded by optional donor tips); built-in CRM | Verified | zeffy.com |
| 25 | H-E-B in DFW | Stores open in Plano, Frisco, Allen, McKinney, Irving etc.; Carrollton store announced | Verified | newsroom.heb.com |
| 26 | Denton County food bank | Served by Tarrant Area Food Bank (transition from NTFB) | Verified | tafb.org |
| 27 | BSV child-care licensing | Texas licensing / exemption rules may apply to a day program for children; exemption 42.041(b)(19) covers some recreation programs ages 5-13 only | Unverified | hhs.texas.gov |
| 28 | Kroger next deadline | Quarterly review; specific next date not confirmed on official page | Unverified | zerohungerzerowastefoundation.org |
| 29 | Walmart FY28 cycles (2027) | Not yet posted; FY27 pattern was Feb-Apr / May-Jul / Aug-Nov | Unverified | walmart.org |
| 30 | Dallas Foundation 2027 dates | Not yet posted | Unverified | dallasfoundation.org |
| 31 | Carrollton CDBG PY2027 dates | Not yet posted | Unverified | cityofcarrollton.com |
| 32 | Diwali 2027 | Late Oct / early Nov 2027 - date not checked | Unverified | - |