## 12-Month Calendar
12-Month Fundraising Calendar (Nov 2026 - Oct 2027)
Goal $ adds up the Master Action Table for each month. Dates checked Oct 13, 2026; '~' = estimate.
Month | Theme | Key dates | Campaigns | Grants / funders | Donor care | Goal $ (from actions)
Nov 2026 | Get ready + first asks | Nov 2 NTxGD reg. opens; Nov 8 Diwali; Nov 26 Thanksgiving; Nov 30 Walmart deadline | Maa's Circle launch; Share a Plate | Walmart; CFT profile | Set up CRM; 48-hr thank-yous start
Dec 2026 | Year-end giving | Dec 1 Giving Tuesday; Dec 31 tax year ends | Giving Tuesday; year-end appeal | Kroger; Albertsons | Holiday cards to top 50 donors
Jan 2027 | Thank + build | Jan 29 year-end statements | Founding Friends (Maa's Place) | NTFB (Jan review); Moody; Meadows | Thank-a-thon calls
Feb 2027 | Ramadan season | ~Feb 8 Ramadan begins; Feb 15 Hoblitzelle window opens | Share a Meal (faith partners); sponsor tiers | Walmart cycle 1 (if repeated) | Impact update #1
Mar 2027 | Maa's Place opens [TBA] | ~Mar 9-10 Eid al-Fitr; Chipotle reopens | Opening event; Founding Friends close | Carrollton CDBG (if open); H-E-B | Tour invites for $250+ donors
Apr 2027 | Dinner prep | Apr 19 Maa's Day campaign starts | Dinner sponsors + tickets | Kroger quarterly | Volunteer appreciation
May 2027 | Maa's Day | May 9 Mother's Day | Maa's Day tributes; Community Dinner | - | Dinner thank-yous in 48 hrs
Jun 2027 | Mid-year | Hoblitzelle 2nd window Jun 15 | Birthday fundraisers | Dallas Foundation summer (if open) | Mid-year impact update
Jul 2027 | Summer needs | - | Summer senior meals appeal | Sprouts (if open) | Monthly donor upgrade ask
Aug 2027 | Giving Day build | ~Late Aug NTxGD early giving | Peer-to-peer pages; match pool | Rees-Jones LOI (BSV, if dated) | Lapsed donor win-back
Sep 2027 | North Texas Giving Day | Sep 16 NTxGD | NTxGD push | - | Thank all NTxGD donors in 48 hrs
Oct 2027 | Review + plan year 2 | Diwali 2027 (date TBC) | Annual impact report | Renewals list | Donor survey
Total

## Master Action Table
Master Action Table
Goal $ = planning estimate. Status dropdown. Nothing is sent or submitted without Aslam's approval.
Month | Activity | Owner | Goal $ | Status | Due / notes | Actual $
Nov 2026 | Fix donate page: real monthly links, custom amount link, program tags on Meals/BSV pages, IRS receipt text | Assistant (draft) / Aslam (approve) | 0 | Not started
Nov 2026 | Request Stripe nonprofit rate (2.2% + 30c) | Aslam | 0 | Not started
Nov 2026 | Set up donor database (Little Green Light) and import Stripe + check/cash records | Assistant / Staff | 0 | Not started
Nov 2026 | Launch Maa's Circle monthly giving (goal: 40 monthly donors by Dec 31) | Aslam / Assistant | 1500 | Not started
Nov 2026 | Walmart Spark Good applications to 2-3 nearby stores (deadline Nov 30) | Assistant (draft) / Aslam (submit) | 5000 | Not started
Nov 2026 | Register for North Texas Giving Day 2027 (opens Nov 2) | Assistant / Aslam | 0 | Not started
Nov 2026 | Complete CFT Nonprofit Gateway Profile | Assistant (draft) / Aslam | 0 | Not started
Nov 2026 | Diwali (Nov 8) + Thanksgiving (Nov 26) 'Share a Plate' with partner temples/businesses | Aslam / Volunteer | 6000 | Not started
Nov 2026 | Recruit 3 board/fundraising committee members | Aslam | 0 | Not started
Dec 2026 | Giving Tuesday Dec 1 (match from 1-2 sponsors) | Aslam / Assistant | 8000 | Not started
Dec 2026 | Year-end appeal: letter + 4 emails (Dec 1, 15, 29, 31) | Assistant (draft) / Aslam | 12000 | Not started
Dec 2026 | Kroger + Albertsons/Nourishing Neighbors requests | Assistant (draft) / Aslam | 3000 | Not started
Dec 2026 | Restaurant give-back night #1 (existing partner) | Volunteer | 800 | Not started
Jan 2027 | Year-end giving statements sent by Jan 29 | Assistant / Aslam | 0 | Not started
Jan 2027 | Thank-a-thon: call every $250+ and every monthly donor | Aslam / Volunteers | 0 | Not started
Jan 2027 | NTFB partner agency application (Jan quarterly review) | Aslam / Staff | 0 | Not started
Jan 2027 | Maa's Place 'Founding Friends' campaign kickoff | Aslam / Staff | 10000 | Not started
Jan 2027 | Moody + Meadows inquiries for Maa's Place | Assistant (draft) / Aslam | 0 | Not started
Feb 2027 | Business sponsorship tiers sent to 20 local businesses (after approval) | Aslam | 15000 | Not started
Feb 2027 | Ramadan 'Share a Meal' with mosques/community partners (~Feb 8-Mar 9) | Aslam | 20000 | Not started
Feb 2027 | Restaurant give-back night #2 | Volunteer | 800 | Not started
Mar 2027 | Carrollton CDBG application (if open, spring 2027) | Assistant (draft) / Aslam | 10000 | Not started
Mar 2027 | Maa's Place opening event + Founding Friends close [date TBA] | Aslam / Staff | 15000 | Not started
Mar 2027 | Chipotle fundraiser application (reopens March) | Volunteer | 0 | Not started
Mar 2027 | H-E-B request for Community Dinner (8+ weeks ahead) | Assistant (draft) / Aslam | 1000 | Not started
Apr 2027 | Community Dinner: venue, sponsors, tickets with quid pro quo disclosure | Aslam / Volunteer lead | 0 | Not started
Apr 2027 | Volunteer appreciation + peer-to-peer captains recruited | Staff | 0 | Not started
Apr 2027 | Restaurant give-back night #3 | Volunteer | 800 | Not started
May 2027 | Maa's Day tribute campaign (Apr 19-May 9) | Assistant / Aslam | 10000 | Not started
May 2027 | Annual Community Dinner 'Love All, Serve All' (net) | Aslam / Volunteer lead | 30000 | Not started
Jun 2027 | Dallas Foundation Summer cycle (if open) | Assistant (draft) / Aslam | 25000 | Not started
Jun 2027 | Mid-year impact update to all donors | Assistant / Aslam | 0 | Not started
Jun 2027 | Restaurant give-back night #4 | Volunteer | 800 | Not started
Jul 2027 | Summer senior meals appeal (heat) | Assistant / Aslam | 5000 | Not started
Jul 2027 | Secure NTxGD match pool from 2-3 sponsors | Aslam | 5000 | Not started
Aug 2027 | NTxGD early giving opens (~late Aug); peer-to-peer pages live | Assistant / Volunteers | 0 | Not started
Aug 2027 | BSV 'Founding Families' case + Rees-Jones LOI (if opening date set) | Assistant (draft) / Aslam | 0 | Not started
Aug 2027 | Restaurant give-back night #5 | Volunteer | 800 | Not started
Sep 2027 | North Texas Giving Day Thu Sep 16 | Aslam / Assistant | 12000 | Not started
Oct 2027 | 12-month review: metrics, donor retention, plan for year 2 | Aslam / Assistant | 0 | Not started
Oct 2027 | Annual impact report + Diwali 2027 drive | Assistant / Aslam | 3000 | Not started
Oct 2027 | Restaurant give-back night #6 | Volunteer | 800 | Not started
Total
Done

## Funders
Funders and Programs (checked Oct 13, 2026)
Verified = program, eligibility and link confirmed on an official page. 'Unverified' text inside a cell means that detail is not confirmed. Do not contact anyone without Aslam's approval.
Verified: |  | Unverified: |  |  | Facts verified: |  | Facts unverified:
# | Funder / program | Category | Fits | What they fund | Typical size | Timing / deadline | Link | Verified? | Watch-outs / eligibility | Next step | Owner | Pipeline status | Last checked | Notes
1 | North Texas Giving Day 2027 (Communities Foundation of Texas) | Giving day | All | Online giving day for nonprofits serving 20 North Texas counties; CFT covers card fees | Depends on our donors + any match pools; est. $5k-$20k | Registration opens Nov 2, 2026; Giving Day Thu Sep 16, 2027 (early giving ~late Aug) | https://www.northtexasgivingday.org/p/registration | Verified | 2027 registration rules/fees not yet posted | Register in Nov 2026; recruit a match sponsor by Jul 2027 | Assistant (prep) / Aslam (submit) | Researching | Oct 13, 2026
2 | Communities Foundation of Texas - Nonprofit Gateway Profile | Community foundation | All | Grants are now nearly all invitation-only; profile puts us on CFT's radar (also DAF holders) | Unverified (third-party listings say $5k-$50k) | Rolling profile; no open application | https://www.cftexas.org/nonprofits/grants/ | Verified | Needs 501(c)(3) active 2+ yrs; 50%+ served in eligible counties | Complete Gateway Profile in Nov 2026 | Assistant (draft) / Aslam | Researching | Oct 13, 2026
3 | The Dallas Foundation - Summer Grants Cycle (Family Economic Stability & Critical Needs) | Community foundation | Meals, Maa's Place | Essential services for children, families, older adults in Dallas County; general operating OK | $5,000-$75,000 (2026 cycle) | 2026 window was Jun 10-26 (closed). 2027 dates not posted - expect ~June 2027 (Unverified) | https://www.dallasfoundation.org/our-impact/grant-opportunities/ | Verified | Over 50% of clients must live in Dallas County; asks for 990, budget, audited financials if available; no event underwriting | Confirm county mix; watch page from Apr 2027 | Assistant | Researching | Oct 13, 2026
4 | The Dallas Foundation - Spring cycle (Specialized Health & Disability) | Community foundation | BSV (later) | 2026 spring focus incl. specialized health & disability programs | Unverified | 2026 window was Jan 14-28; 2027 not posted | https://www.dallasfoundation.org/our-impact/grant-opportunities/ | Verified | 2026 spring cycle required org budget over $500,000; BSV not open yet | Revisit after BSV opens | Assistant | Researching | Oct 13, 2026
5 | The Meadows Foundation - Human Services | Private foundation | Meals, Maa's Place | Programs that improve quality of life for vulnerable Texans; up to 50% of giving in DFW | Unverified | Rolling; submit 4-5 months before funds are needed; monthly info sessions | https://www.mfi.org/how-to-apply/ | Verified | Wants measurable outcomes and other funding secured | Attend an info session; call program officer (Aslam's decision) | Aslam / Assistant | Researching | Oct 13, 2026
6 | The Rees-Jones Foundation | Private foundation | BSV (children & families) | DFW children, youth and their families (and companion animals) within defined portfolios | Unverified | Rolling Letter of Inquiry; ~30 days to invite/decline; ~4 months staff review | https://www.rees-jonesfoundation.org/apply-for-funding/ | Verified | Must match a portfolio; BSV must be operating | Check portfolio fit; LOI after BSV opening date is set | Assistant | Researching | Oct 13, 2026
7 | The Moody Foundation - General Grant Inquiry | Private foundation | All | Texas: education, social services & family well-being, health & wellness, arts | Unverified | Rolling inquiry; up to ~6 months to decision; 4 trustee meetings/yr | https://moodyf.org/application-process/ | Verified | One active inquiry per organization | Submit one inquiry (Maa's Place opening) in Jan 2027 | Assistant (draft) / Aslam | Researching | Oct 13, 2026
8 | Hoblitzelle Foundation | Private foundation | Maa's Place / BSV capital | Capital only: buildings, renovation, equipment, vehicles, technology (Dallas area priority) | Unverified | Windows Feb 15-Apr 15, 2027 and Jun 15-Aug 15, 2027 | https://hoblitzelle.org/how-to-apply | Verified | Requires annual budget over $250,000 AND external audit within 2 years - likely NOT eligible yet | Ask Aslam: budget size and audit status | Aslam | Researching | Oct 13, 2026
9 | Crystal Charity Ball | Charity / foundation | BSV (future) | Dallas County children's charities; large multi-year project grants | Unverified | 2027 cycle closed Oct 8, 2026; next cycle ~Aug-Oct 2027 | https://crystalcharity.org/apply-for-funding/ | Verified | Must have served Dallas County children 3+ years - BSV not eligible until ~3 yrs after opening | Long-term only | Assistant (track) | Researching | Oct 13, 2026
10 | Walmart Spark Good Local Grants | Corporate | Meals | Local store/Sam's Club/DC grants; hunger relief is a frequent area of support | $250-$5,000 | FY27 Cycle 3: Aug 1-Nov 30, 2026 (open now). Cycles 1-2 were Feb 1-Apr 15, May 1-Jul 15 | https://walmart.org/how-we-give/program-guidelines/spark-good-local-grants-guidelines | Verified | Needs Spark Good account + Deed verification; one award per facility per fiscal year | Apply to 2-3 Carrollton-area stores by Nov 30, 2026 | Assistant (draft) / Aslam (submit) | Researching | Oct 13, 2026
11 | Kroger Zero Hunger ¦ Zero Waste Foundation + Kroger store giving | Corporate | Meals | Hunger relief, mobile pantries, food access; stores also give cash/gift cards/product | Unverified | Applications reviewed quarterly (exact 2026-27 dates Unverified) | https://zerohungerzerowastefoundation.org/how_we_give.html | Verified | Kroger Dallas Division store requests go through the Kroger proposal portal (thekrogerco.versaic.com) | Submit one request in Dec 2026 | Assistant (draft) / Aslam | Researching | Oct 13, 2026
12 | Albertsons Companies Foundation / Nourishing Neighbors (Tom Thumb, Albertsons) | Corporate | Meals | Hunger relief; Innovation Incubation Fund for new food-security ideas | Unverified | Rolling; reviewed monthly (per Nourishing Neighbors RFP page) | https://www.nourishingneighbors.com/ | Verified | Must serve communities with an Albertsons-family store (Tom Thumb is in DFW); a local Tom Thumb in-kind/gift-card process is Unverified | Check current open RFP; ask local Tom Thumb manager about product donations | Assistant / Volunteer | Researching | Oct 13, 2026
13 | H-E-B My Community Investment (H-E-B, Central Market, Joe V's) | Corporate | Meals, events | Hunger relief, community; not operating expenses or third-party fundraisers | Under $200 in store; larger online | Apply 8+ weeks before decision needed; re-apply yearly | https://newsroom.heb.com/donation-guidelines/ | Verified | H-E-B has opened stores in DFW (Plano, Frisco, Irving etc.) and has announced a Carrollton store; one request per event | Request food/gift cards for Community Dinner (apply by Mar 2027) | Assistant (draft) / Aslam | Researching | Oct 13, 2026
14 | Sprouts Healthy Communities Foundation - Neighborhood Grants | Corporate | Meals, Maa's Place | Nutrition security, adult wellness, children's nutrition education | Up to $5,000 | 2026 window closed Jun 1; 2027 window not announced (Unverified) | https://www.sprouts.com/about/sprouts-foundation/ | Verified | Healthy Communities ($50k-$100k) is invitation-only after a Neighborhood Grant | Watch for spring 2027 window | Assistant | Researching | Oct 13, 2026
15 | Costco local warehouse donation | Corporate | Meals | Children, education, health & human services; monetary requests via printed form at warehouse | Small; exact amounts Unverified | 4-6 weeks ahead; one request per fiscal year (Sep-Aug) | https://www.costco.com/charitable-giving.html | Verified | Amounts not stated on official page | Drop off form at nearest warehouse (Volunteer) | Volunteer | Researching | Oct 13, 2026
16 | Texas Instruments Foundation | Corporate | All | Greater Dallas; human services among priorities; mostly by invitation | Unverified | No open cycle; introduce via giving@ti.com | https://www.ti.com/about-ti/citizenship-community/giving/eligible-organizations.html | Verified | Unsolicited proposals generally not considered | Aslam decides whether to send intro email | Aslam | Researching | Oct 13, 2026
17 | Toyota Motor North America / Toyota USA Foundation (Plano) | Corporate | All | Community grants by invitation only (invitation code) | Unverified | Invitation only | https://www.toyotaeffect.com/grant-seekers/ | Verified | No unsolicited applications | Build relationship via Toyota employee volunteers | Aslam | Researching | Oct 13, 2026
18 | AT&T Foundation + AT&T employee giving | Corporate | All | Foundation is invitation only; employee gifts matched 1:1 up to $1,000/yr; volunteer grants | Up to $1,000 per employee | Anytime (employee-initiated) | https://giving.att.com/ | Verified | Match/volunteer grant figures from AT&T sustainability page (via search) | Ask donors/volunteers who work at AT&T to submit matches | Staff | Researching | Oct 13, 2026
19 | Chipotle Community Fundraisers | Restaurant give-back | Meals | 25% of qualifying sales from a fundraiser night (min. $150 sales) | Typically a few hundred $ per night | 2026 applications closed; reopen March 2027 | https://community.chipotle.com/faq/ | Verified | Local partner restaurants (Al Markaz, Popeyes franchise, Chef Chen) are better first choices | Apply Mar 2027 | Volunteer | Researching | Oct 13, 2026
20 | City of Carrollton CDBG - Social/Public Services | Government (local) | Meals, Maa's Place | HUD CDBG for low-to-moderate income Carrollton residents; public services capped at 15% (~$113,000) | Pool ~$113,000 (PY2026 went entirely to Metrocrest Services) | PY2026: apps Mar 19-May 1, 2026. PY2027 dates not posted - expect spring 2027 (Unverified) | https://www.cityofcarrollton.com/departments/departments-a-f/community-development/community-development-block-grant-cdbg | Verified | Competitive; must document Carrollton low/mod-income clients | Call Community Development (972-466-4299) in Feb 2027 - Aslam | Aslam / Assistant | Researching | Oct 13, 2026
21 | North Texas Food Bank - Partner Agency (incl. TEFAP & senior programs) | Food bank | Meals, Maa's Place | Low-cost/free food, USDA TEFAP commodities, produce; CSFP senior boxes distributed by NTFB | In-kind (could cut food cost substantially) | Applications reviewed quarterly: Jan, Apr, Jul, Oct | https://ntfb.org/partner-agency/ | Verified | Clients in Dallas, Collin (and 10 other) counties - NOT Denton; needs food storage, food-safety rules | Confirm county of sites/clients; apply for Jan 2027 review | Aslam / Staff | Researching | Oct 13, 2026
22 | Tarrant Area Food Bank - Partner Agency (TAFB North serves Denton County) | Food bank | Meals | Partner agencies in 13 counties incl. Denton; meal programs need health permits | In-kind | Rolling (submit prospective partner form) | https://tafb.org/partners/ | Verified | Must serve 6+ months; shared maintenance fees; monthly reports | Use only if clients/site are in Denton County | Staff | Researching | Oct 13, 2026
23 | Dallas Area Agency on Aging (Community Council of Greater Dallas) | Government (OAA Title III) | Maa's Place, Meals (seniors) | Older Americans Act Title III services for Dallas County 60+ via subrecipients | Unverified | No open RFP found (Unverified) | https://www.ccadvance.org/daaa | Verified | Title III providers must meet state AAA rules; realistic year-1 step is partnership/referrals | Request intro meeting (Aslam's decision) | Aslam | Researching | Oct 13, 2026
24 | North Central Texas Area Agency on Aging (NCTCOG) - Denton & Collin | Government (OAA Title III) | Maa's Place, Meals (seniors) | 14-county AAA; Denton County meals provider is SPAN, Inc.; Collin is Meals on Wheels of Collin County | Unverified | No open RFP found (Unverified) | https://www.nctcog.org/aging-services/older-adults/contract-services | Verified | Funding goes to contracted providers; partnership/referral more realistic in year 1 | Ask about referrals to Maa's Place | Aslam | Researching | Oct 13, 2026
25 | Texas HHS - Area Agency on Aging nutrition rules (Title III pass-through) | Government (state) | Seniors | State oversight of AAA nutrition programs (not a direct grant) | n/a | n/a | https://www.hhs.texas.gov/handbooks/area-agency-aging-policies-procedures-manual/f-1500-administration-nutrition-programs | Verified | No direct application; money flows through AAAs | Reference only | Assistant | Researching | Oct 13, 2026
26 | Rotary Club of Carrollton-Farmers Branch | Civic club | All | Annual community-service grants to local nonprofits (e.g., Metrocrest Services, senior services) | Unverified | Unverified (annual) | https://cfbrotary5810.org/Stories/carrollton-farmers-branch-rotary-club-supports-valuable-community-organizations | Verified | Application process/size not posted | Ask to present at a meeting; volunteers join a Saturday shift | Aslam | Researching | Oct 13, 2026
27 | Carrollton-area Lions Club(s) | Civic club | All | Service projects (vision, youth) | Unverified | Unverified | (no official page found) | Unverified | No official grant page found | Ask a member contact; low priority | Volunteer | Researching | Oct 13, 2026
28 | Faith communities (mosques, temples, churches, gurdwaras in DFW) | Faith partners | All | Ramadan, Diwali, Thanksgiving and year-end drives; volunteer teams; in-kind | $1k-$15k per partner drive (estimate) | Ramadan ~Feb 8-Mar 9, 2027 (moon-sighting); Diwali Nov 8, 2026 | (no official page found) | Unverified | Partner names to come from Aslam; keep public posts non-religious | Aslam lists 10 partners; Assistant drafts asks | Aslam | Researching | Oct 13, 2026
29 | Donor-advised funds (Fidelity Charitable, Schwab, CFT, NPT etc.) | DAF | All | Donors recommend grants from their DAF; needs our legal name + EIN on the website | Varies | Peak Nov-Dec | (no official page found) | Unverified | Specific DAF-button tools/pricing not checked | Add 'Give from your DAF' text (EIN 86-2221897) to donate page | Assistant | Researching | Oct 13, 2026
30 | United Way of Denton County - Community Impact Grants | United Way | Low fit | Youth, workforce, veterans, homelessness, behavioral health | Unverified | Unverified | https://www.unitedwaydenton.org/community-impact-grants | Verified | Focus areas do not match hunger/seniors well | Low priority | Assistant (track) | Researching | Oct 13, 2026
Fact-check log (rules, dates, prices)
# | Item | Finding |  | Finding |  |  | Source | Status
1 | North Texas Giving Day 2026 date |  |  | Thu Sep 17, 2026 (already passed) |  |  | https://www.northtexasgivingday.org/p/AboutUs | Verified
2 | North Texas Giving Day 2027 date |  |  | Thu Sep 16, 2027 |  |  | https://www.cftexas.org/about-cft/blog-and-newsroom/north-texas-giving-day-2026/ | Verified
3 | NTxGD 2027 registration |  |  | Opens Nov 2, 2026 |  |  | https://www.northtexasgivingday.org/p/registration | Verified
4 | Giving Tuesday 2026 |  |  | Tue Dec 1, 2026 (day after Thanksgiving week; Thanksgiving Nov 26) |  |  | Calendar | Verified
5 | Diwali 2026 |  |  | Sun Nov 8, 2026 |  |  | https://globalpanchang.com/diwali | Verified
6 | Ramadan 2027 |  |  | Expected to start ~Mon Feb 8, 2027; Eid al-Fitr ~Mar 9-10 (moon-sighting) |  |  | https://www.khaleejtimes.com/uae/ramadan-eid-al-fitr-eid-al-adha-2027-likely-dates | Unverified
7 | Mother's Day 2027 |  |  | Sun May 9, 2027 |  |  | Calendar | Verified
8 | Texas raffles: who can hold them |  |  | 501(c) nonprofit in existence 3+ years (plus religious societies 10+ yrs, volunteer fire/EMS) |  |  | https://www.texasattorneygeneral.gov/divisions/charitable-trusts/charitable-raffles-and-casinopoker-nights | Verified
9 | Texas raffles: how many |  |  | Up to 4 per calendar year (changed from 2 in June 2021 by HB 2757) |  |  | https://www.texasattorneygeneral.gov/divisions/charitable-trusts/charitable-raffles-and-casinopoker-nights | Verified
10 | Texas raffles: prizes |  |  | No cash prizes; purchased prize max $75,000; donated prizes no limit; must own prize or post bond |  |  | https://statutes.capitol.texas.gov/Docs/OC/htm/OC.2002.htm | Verified
11 | Texas raffles: selling |  |  | No statewide promotion or ticket sales (generally read to include the internet); no paid organizers; 5 items on each ticket |  |  | https://www.texasattorneygeneral.gov/divisions/charitable-trusts/charitable-raffles-and-casinopoker-nights | Verified
12 | Casino/poker night fundraisers |  |  | Not allowed for nonprofits in Texas |  |  | https://www.texasattorneygeneral.gov/divisions/charitable-trusts/charitable-raffles-and-casinopoker-nights | Verified
13 | IRS raffle prize reporting |  |  | W-2G if prize minus ticket price is at least $2,000 (2026 threshold) and 300x the ticket; 24% withholding over $5,000 |  |  | https://www.irs.gov/instructions/iw2g | Verified
14 | IRS written acknowledgment |  |  | Needed for any single gift of $250+; must say whether goods/services were given |  |  | https://www.irs.gov/charities-non-profits/charitable-organizations/charitable-contributions-written-acknowledgments | Verified
15 | IRS quid pro quo disclosure |  |  | Required when a payment over $75 is partly a gift and partly goods/services |  |  | https://www.irs.gov/charities-non-profits/substantiating-charitable-contributions | Verified
16 | IRS Publication 1771 |  |  | Charity guide to substantiation and disclosure |  |  | https://www.irs.gov/pub/irs-pdf/p1771.pdf | Verified
17 | Texas tax-free sales/auctions |  |  | Two one-day tax-free sales or auctions per calendar year (needs Texas exemption, Form AP-204) |  |  | https://comptroller.texas.gov/taxes/publications/96-122.php | Verified
18 | Stripe nonprofit rate |  |  | 2.2% + 30c for eligible 501(c)(3)s with 80%+ donation volume; request via Stripe support / nonprofit@stripe.com |  |  | https://support.stripe.com/questions/fee-discount-for-nonprofit-organizations | Verified
19 | Little Green Light price |  |  | $45/mo up to 2,500 records; unlimited users; 10% off annual |  |  | https://www.littlegreenlight.com/pricing/ | Verified
20 | LGL + Stripe |  |  | LGL Forms accept Stripe; Zapier Stripe-to-LGL zaps exist |  |  | https://help.littlegreenlight.com/article/373-enable-your-lgl-forms-account-to-accept-stripe-payments | Verified
21 | Bloomerang price |  |  | Starts at $125/mo billed annually |  |  | https://bloomerang.com/pricing | Verified
22 | DonorPerfect price |  |  | Core plan from ~$99-$119/mo (sources differ) |  |  | https://www.donorperfect.com/fundraising-software/pricing-guide/ | Unverified
23 | Givebutter price |  |  | Free with optional donor tips; 3% platform fee if tips off; Plus from $29/mo |  |  | https://givebutter.com/pricing | Verified
24 | Zeffy price |  |  | Free to nonprofits (funded by optional donor tips); built-in CRM |  |  | https://www.zeffy.com/home/free-online-fundraising-platform | Verified
25 | H-E-B in DFW |  |  | Stores open in Plano, Frisco, Allen, McKinney, Irving etc.; Carrollton store announced |  |  | https://newsroom.heb.com/h-e-b-opens-store-in-irving-as-part-of-continued-dfw-area-expansion/ | Verified
26 | Denton County food bank |  |  | Served by Tarrant Area Food Bank (transition from NTFB) |  |  | https://tafb.org/news/transition-of-denton-county-services/ | Verified
27 | BSV child-care licensing |  |  | Texas licensing / exemption rules may apply to a day program for children; exemption 42.041(b)(19) covers some recreation programs ages 5-13 only |  |  | https://www.hhs.texas.gov/providers/child-care-regulation/become-a-provider/ccr-licensing-exemptions | Unverified
28 | Kroger next deadline |  |  | Quarterly review; specific next date not confirmed on official page |  |  | https://zerohungerzerowastefoundation.org/how_we_give.html | Unverified
29 | Walmart FY28 cycles (2027) |  |  | Not yet posted; FY27 pattern was Feb-Apr / May-Jul / Aug-Nov |  |  | https://walmart.org/how-we-give/program-guidelines/spark-good-local-grants-guidelines | Unverified
30 | Dallas Foundation 2027 dates |  |  | Not yet posted |  |  | https://www.dallasfoundation.org/our-impact/grant-opportunities/ | Unverified
31 | Carrollton CDBG PY2027 dates |  |  | Not yet posted |  |  | https://www.cityofcarrollton.com/departments/departments-a-f/community-development/community-development-block-grant-cdbg | Unverified
32 | Diwali 2027 |  |  | Late Oct / early Nov 2027 - date not checked |  |  | - | Unverified

## Budget
Budget (placeholders - Aslam to fill the yellow cells)
Annual = one-time + 12 x monthly. Org placeholders: Annual operating budget [$], Amount raised last year [$], Number of donors [#], 12-month goal [$].
Annual operating budget [$] |  |  | Amount raised last year [$]
Number of donors [#] |  |  | 12-month goal [$]
A. Maa's Place + Blooming Star Village | MP one-time | MP monthly | MP annual | BSV one-time | BSV monthly | BSV annual | Notes
Lease deposit / rent
Build-out, accessibility, safety | [6 empty] | Ramps, grab bars, sensory room
Furniture, chairs, tables
Kitchen / snack and chai equipment
Activity and sensory supplies
Snacks, chai, fruit
Utilities, internet, phone
Insurance (GL, D&O, accident; abuse & molestation for BSV) | [6 empty] | Get 2 quotes
Background checks, training, first aid/CPR
Licensing / exemption costs (BSV) | [6 empty] | Check Texas HHS child-care rules
Coordinator / specialist staff (if any) | [6 empty] | See 'no salaries' question
Cleaning, maintenance
Signage, printing
Other
Total
B. Fundraising costs (12 months) | Low | High | Actual |  |  |  | Notes
Little Green Light CRM ($45/mo) | 540 | 540 |  |  |  |  | Verified price Oct 13, 2026
Printing and postage | 1500 | 3000
Community Dinner (offset by sponsors) | 5000 | 15000
Maa's Place opening event | 500 | 2000
Sponsor kit, banners, signs | 300 | 800
North Texas Giving Day | 0 | 300 |  |  |  |  | CFT covers card fees
Stripe fees | [6 empty] | 2.2% + 30c if nonprofit rate approved
Total fundraising costs
C. Revenue estimates by source (12 months) | Low | High | Midpoint | Goal (set) | Actual
Monthly giving circle (Maa's Circle) | 8000 | 30000 |  |  |  |  | Cost: ~$0 (Stripe fees) · Owner: Aslam / Assistant
Giving Tuesday + year-end appeal | 8000 | 25000 |  |  |  |  | Cost: $500-$1,500 print/postage · Owner: Aslam / Assistant
Maa's Place opening campaign | 15000 | 50000 |  |  |  |  | Cost: $500-$2,000 event · Owner: Aslam / Staff
Ramadan 'Share a Meal' with faith partners | 10000 | 40000 |  |  |  |  | Cost: $200-$800 · Owner: Aslam
Diwali + Thanksgiving 'Share a Plate' | 3000 | 12000 |  |  |  |  | Cost: $200-$500 · Owner: Aslam / Volunteer
Maa's Day (Mother's Day tribute) campaign | 5000 | 20000 |  |  |  |  | Cost: $300-$800 · Owner: Assistant / Aslam
Annual Community Dinner (net) | 15000 | 45000 |  |  |  |  | Cost: $5,000-$15,000 · Owner: Aslam / Volunteer lead
North Texas Giving Day 2027 | 5000 | 20000 |  |  |  |  | Cost: $0-$300 · Owner: Assistant / Aslam
Business sponsors (local) | 10000 | 40000 |  |  |  |  | Cost: $300 sponsor kit · Owner: Aslam
Corporate/retail grants | 2000 | 20000 |  |  |  |  | Cost: Staff time · Owner: Assistant / Aslam
Foundation grants | 0 | 75000 |  |  |  |  | Cost: Staff time · Owner: Assistant / Aslam
Peer-to-peer + birthday fundraisers | 2000 | 10000 |  |  |  |  | Cost: $0 · Owner: Volunteer / Assistant
Restaurant give-back nights (x6) | 1500 | 6000 |  |  |  |  | Cost: $0-$200 · Owner: Volunteer
Civic clubs + faith grants | 1000 | 7500 |  |  |  |  | Cost: $0 · Owner: Aslam
Employer matching + volunteer grants | 1000 | 5000 |  |  |  |  | Cost: $0 · Owner: Staff
Total
Cost per dollar raised (estimate, using midpoint)

## Metrics
Key Metrics (enter yellow cells monthly; grey rows calculate)
Targets from the plan. Update by the 10th of each month.
Metric | Target | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | 12-mo total
Total raised ($)
Number of gifts
Unique donors
New donors
Active monthly donors (month end) | 100
Monthly recurring revenue ($) | 3000
Fundraising costs ($)
Gifts thanked within 48 hrs
Lapsed donors reactivated
Grants submitted | 10
Grants won | 4
Meals served
Meal costs ($)
Average gift ($)
Cost per dollar raised ($) | 0.2
48-hour thank-you rate | 95%
Grant win rate | 35%
Cost per meal ($) | 5
Yearly retention
Donors who gave last year (Nov 2025 - Oct 2026)
Of those, donors who gave again this year
First-time donors (12 months)
Of those, gave a second gift
Donor retention (target 50%+)
New-donor retention (target 35%+)