Maa's Inspiration – Fundraising Top 10 (Nov 2026 – Oct 2027)

Ranked by expected return vs. effort (best first). $ ranges are planning estimates from the full plan, not promises; '—' = no $ estimate in the plan. Next 90 days: Nov 2 North Texas Giving Day registration opens · Nov 30 Walmart Spark Good deadline · Dec 1 Giving Tuesday · Dec 31 year-end.

1. Campaigns & events

| What | Expected $ | Effort | When | Owner |
| --- | --- | --- | --- | --- |
| Fix donate page + add monthly ask | Enables every campaign; — | Low | Nov 2026 | Assistant + Aslam |
| Maa's Circle monthly giving ($25/mo = 5 meals) | $8,000–$30,000 | Low | Launch Nov 2026 | Aslam / Assistant |
| Giving Tuesday + year-end appeal | $8,000–$25,000 | Med | Dec 1–31, 2026 | Aslam / Assistant |
| Ramadan 'Share a Meal' with faith partners | $10,000–$40,000 | Med | ~Feb 8–Mar 9, 2027 | Aslam |
| Maa's Place 'Founding Friends' opening campaign | $15,000–$50,000 | Med | Jan–Mar 2027 (opening date TBA) | Aslam / Staff |
| Local business sponsor tiers | $10,000–$40,000 | Med | Jan–Mar 2027 | Aslam |
| Maa's Day (Mother's Day) tribute gifts | $5,000–$20,000 | Low | Apr 19–May 9, 2027 | Assistant / Aslam |
| Diwali + Thanksgiving 'Share a Plate' | $3,000–$12,000 | Low | Nov 2026 | Aslam / Volunteer |
| Sponsor-a-Senior ($25/week pack) | — | Low | Thanksgiving + Mother's Day | Assistant |
| Community Dinner 'Love All, Serve All' | $15,000–$45,000 net | High | May 2027 | Aslam + Volunteer lead |

2. Funders, grants & corporate (verified only)

| What | Expected $ | Effort | When | Owner |
| --- | --- | --- | --- | --- |
| Walmart Spark Good Local Grants (2–3 Carrollton stores) | $250–$5,000 per award | Low | Apply by Nov 30, 2026 | Assistant drafts / Aslam submits |
| North Texas Giving Day 2027 | $5,000–$20,000 | Med | Register from Nov 2, 2026; day is Sep 16, 2027 | Assistant / Aslam |
| North Texas Food Bank partner agency (if sites/clients are in Dallas County) | In-kind food (no $ figure) | Med | Jan 2027 review | Aslam / Staff |
| Dallas Foundation Summer cycle (needs 50%+ Dallas County clients) | $5,000–$75,000 | High | ~Jun 2027 (dates not posted) | Assistant / Aslam |
| Kroger Zero Hunger ¦ Zero Waste request | Not stated by funder | Med | Dec 2026 | Assistant / Aslam |
| Albertsons / Nourishing Neighbors (Tom Thumb) | Not stated by funder | Med | Dec 2026 | Assistant / Volunteer |
| H-E-B donation request (Community Dinner) | Under $200 in store; larger online | Low | Apply by Mar 2027 | Assistant / Aslam |
| Meadows Foundation – Human Services | Not stated by funder | High | Rolling (inquiry Jan 2027) | Aslam / Assistant |
| Moody Foundation inquiry (Maa's Place) | Not stated by funder | High | Jan 2027 | Assistant / Aslam |
| City of Carrollton CDBG public services | Competitive pool ~$113,000 | High | Spring 2027 (dates not posted) | Aslam / Assistant |

3. Existing donors

| What | Expected $ | Effort | When | Owner |
| --- | --- | --- | --- | --- |
| Thank every gift within 48 hours | — | Low | Starting now | Staff / Assistant |
| Aslam calls every gift of $250+ | — | Low | Starting now | Aslam |
| Ask repeat donors to become monthly (Maa's Circle) | Part of $8,000–$30,000 | Low | Nov 2026, then monthly | Assistant / Aslam |
| Employer matching (e.g. AT&T 1:1 up to $1,000) | $1,000–$5,000 | Low | Any time | Staff |
| Peer-to-peer + birthday fundraisers | $2,000–$10,000 | Low | Year-round | Volunteer / Assistant |
| Holiday cards to top 50 donors | — | Low | Dec 2026 | Aslam |
| Year-end giving statements | — | Low | By Jan 29, 2027 | Assistant / Aslam |
| Thank-a-thon: call $250+ and monthly donors | — | Med | Jan 2027 | Aslam / Volunteers |
| Major donors: quarterly personal touch | — | Med | Quarterly | Aslam |
| Lapsed donor win-back letter + call | — | Med | Twice a year (Aug 2027) | Staff / Aslam |

4. Follow-up & processes

| What | Expected $ | Effort | When | Owner |
| --- | --- | --- | --- | --- |
| IRS-compliant receipt wording for gifts of $250+ | — | Low | Nov 2026 | Assistant / Aslam |
| Thank-you rules by gift size (email, note, call) | — | Low | Starting now | Staff / Aslam |
| Donor database: Little Green Light linked to Stripe | Costs $45/month | Med | Nov 2026 | Assistant / Staff |
| 90-day follow-up series for new donors | — | Med | Nov 2026 | Assistant / Staff |
| Monday 30-minute fundraising checklist | — | Low | Weekly | Aslam / Staff |
| Monthly metrics report (by the 10th) | — | Low | Monthly | Assistant |
| Grant 'ready folder' + grant tracking process | — | Med | Nov 2026 | Assistant |
| Monthly match: Stripe, QuickBooks and donor database | — | Med | Monthly | Staff |
| Mid-year impact update to all donors | — | Low | Jun 2027 | Assistant / Aslam |
| 12-month review and year-2 plan | — | Med | Oct 2027 | Aslam / Assistant |

5. Other / foundation setup

| What | Expected $ | Effort | When | Owner |
| --- | --- | --- | --- | --- |
| Fill in key numbers: budget, raised last year, donors, goal | — | Low | Now | Aslam |
| Request Stripe nonprofit rate (2.2% + 30¢) | Lower card fees | Low | Nov 2026 | Aslam |
| Add 'Give from your DAF' text with EIN to donate page | Varies | Low | Nov 2026 | Assistant |
| Confirm county of sites and clients (unlocks food bank + Dallas Foundation) | — | Low | Nov 2026 | Aslam |
| Complete CFT Nonprofit Gateway Profile | Unverified | Low | Nov 2026 | Assistant / Aslam |
| List 10 faith/community partners | — | Low | Nov 2026 | Aslam |
| Present at Rotary Club of Carrollton-Farmers Branch | Civic + faith grants $1,000–$7,500 | Low | Winter 2026–27 | Aslam |
| Check Texas sales-tax exemption (Form AP-204) | — | Low | Nov 2026 | Aslam |
| Recruit 3 board / fundraising committee members | — | Med | Nov 2026 | Aslam |
| Gather Form 990 + financial statements for grants | — | Med | Dec 2026 | Aslam / Assistant |